## The BIG Six
The BIG Six | Status Quo | 2026 Strategic Objective | The Focus | PIC | Which belong to which Focus | Which belong to which Priority
1. Income Dependency (Profitability Risk) | Our revenue model relies heavily on a single client who contributes 77.7% of annual income in 2025. Why this matters: Over-reliance increases business risk and limits financial resilience. | Reduce dependency on a single client by increasing diversified revenue to at least 70% of total income. | Improve Client & Project Retention Increase client retention by strengthening service quality and delivering consistently excellent customer experience. | OPS, EXP | Company Profitability - Customer Retention | Company Profitability
|  |  | Increase Upsell & Cross-Sell to Existing Customers Expand revenue from current clients by offering additional human resources (upsell) and complementary services (cross-sell). | OPS, EXP, MNG | Company Profitability - Customer Retention | Company Profitability
|  |  | Launch Commission-Based Sales Program Introduce and test commission-based sales roles in the USA and Europe to drive higher accountability and customer acquisition. | GRW, MNG | Company Profitability - Customer Acquisition | Company Profitability
|  |  | Create Referral Program Develop an attractive referral program to generate new client leads through existing relationships. | GRW, EXP, MNG | Company Profitability - Customer Acquisition | Company Profitability
|  |  | Leverage Indonesia-Based Projects Utilize Indonesian project opportunities to build a stronger service portfolio and establish workflows for potential new markets. | GRW, OPS, MNG, EXP, HRD | Company Profitability - Customer Acquisition | Company Profitability
|  |  | Monitor Industry Trends Monitor and track evolving industry trends to identify emerging demands and refine our positioning as a niche expert agency. | GRW, MNG | Company Establishment - Branding, Communication & Experience | Company Establishment
2. Business Development | Our current services and markets are limited to: Services: 1. Outbound Account & Lead Generation Email Marketing CRM Tool Management Data Cleaning & Data Appending 2. Inbound Social Media Management Market: 1. Industry Biotech Robotics (Devonics) Fintech (FxPro) SaaS (Trialist) 2. Geography United States Canada United Kingdom France Germany Norway Netherlands Vietnam Indonesia Singapore Why this matters: |  | Restructure the Growth Department - Build a focused Business Development team to research, validate, and coordinate all Market Penetration, Service Development, and Market Expansion initiatives. - Redefine Growth Dept structure that better fits the evolving needs and demands of the company based on the past and existing performance. | MNG, HRD, GRW | Company Establishment - Organizational Structure | Company Establishment
|  |  | Drive Market Development Expand into new markets by conducting targeted sales efforts that introduce our existing services to new industries or regions. | GRW, OPS, MNG | Company Profitability - Business Development | Company Profitability
|  |  | Advance Service Development Develop new digital marketing services for existing markets and prepare the required talent, tools, and processes to deliver them effectively. | GRW, OPS, EXP, MNG, HRD, ITE | Company Profitability - Business Development | Company Profitability
|  |  | Execute Diversification Strategy Develop new digital marketing services / products for new markets and build the foundational capabilities needed to operate in those new segments. | GRW, MNG | Company Profitability - Business Development | Company Profitability
|  |  | Drive Technology Innovation Establish a specialized team to lead technology innovation, including infrastructure upgrades, data security improvements, and step-by-step implementation of new tech capabilities. | ITE, GRW, OPS, MNG, HRD | Company Establishment - Technology Innovation | Company Establishment | EA's note: Ini kalo Operations & IT menyanggupi, boleh sekalian include rencana perbaikan data Operations di 2026 dalam rangka BigQuery Database Preparation, including: Need Analysis Format Standardization Data Cleaning Data Relationship Mapping BigQuery Subscription Data Upload Data Integration Interface Integration (to Masterlist, to Looker)
3. Scalability | Our current operations and HR management systems are inefficient for serving multiple SMEs simultaneously. Why this matters: |  | Refine Operations Playbook Evaluate and document the execution of Operations General Playbook and the successful rate with the end goal of refining the process in the next projects. | OPS | Company Profitability - Customer Retention | Company Profitability
|  |  | Scale Client Satisfaction Set Up Client Satisfaction Systems that Scale for Experience & Operations Dept by defining and launching the Three Experience Tiers: Improve client's experience that is more integrated and standardized. | EXP, OPS, MNG | Company Profitability - Customer Retention | Company Profitability
4. FBA Ecosystem | We currently lack a functional, profitable FBA business that strategically integrates with Horizon. Why this matters: Without a working and profitable FBA arm, we miss a key opportunity to diversify revenue beyond services, reduce dependency on client-based income / LeadGeeks Inc., and build a scalable asset that strengthens LeadGeeks’ long-term resilience and growth. | Achieve Commercial Validation & Operational Stability by launching and running the Amazon FBA business, confirming that the products can sell profitably, and setting up clear, repeatable operating processes. | FBA Business Model Deepening & Validation Validate and deepen the FBA business model by applying learned frameworks to real product decisions, cost see-through, pricing logic, and Amazon mechanics in live execution in order to confirm commercial viability and scalability. | FBA, MNG | Company Profitability - Business Development | Company Profitability
|  |  | FBA Business Development Execution Execute the approved FBA Business Development Plan by launching selected SKUs, implementing pricing, logistics, and go-to-market strategy in order to generate initial sales and real performance data. | FBA, MNG | Company Profitability - Business Development | Company Profitability
|  |  | Operational Stability & SOP Establishment Establish stable FBA operational workflows by documenting SOPs for sourcing, prep, shipment, listing updates, and issue handling in order to ensure repeatable and low-risk execution. | FBA, MNG | Company Profitability - Business Development | Company Profitability
|  |  | FBA Team Capability Strengthening Strengthen FBA team capability by clarifying ownership, expanding responsibilities, and improving decision autonomy in order to reduce Top Management dependency and increase execution speed. | FBA, MNG | Company Profitability - Business Development | Company Profitability
|  |  | Performance Review & Optimization Loop Evaluate FBA performance holistically by reviewing sales, costs, ads efficiency, ops issues, and customer feedback in order to optimize strategy, decide scale / pause / adjust actions. | FBA, MNG | Company Profitability - Business Development | Company Profitability
5. Brand Awareness | We currently lack brand presence both from the company branding (LeadGeeks Inc.) and employer branding (Amanda) |  | Boost Brand Presence Strengthen LeadGeeks Inc. brand includes the online presence performance (new website, LinkedIn) with stronger and clearer Positioning & Messaging. | GRW, MNG, ITE | Company Profitability - Customer Acquisition | Company Profitability
|  |  | Attend On-Site Tradeshows Attend relevant tradeshows in USA & Europe as exhibitors to promote LeadGeeks Inc. brand, build the list of potential clients, and connect offline with existing clients | GRW, MNG, EXP | Company Profitability - Customer Acquisition | Company Profitability
|  |  | Promote Amanda’s LinkedIn Presence Promote Amanda LinkedIn account to attract potential clients. Stay active on Amanda LinkedIn account as the main magnet for all stakeholders. | MNG, HRD, GRW, EXP | Company Profitability - Customer Acquisition | Company Profitability
6. Shared Goals with Parent Company | The company plans to establish a parent company that becomes the umbrella of LeadGeeks Inc. and Alunara. |  | Start Succession Planning Start the succession planning program for critical roles that impact the business such as Mission-Critical Positions, Positions With High Impact on Business, Hard-to-Recruit or Hard-to-Replace Roles, Roles With High Turnover Risk, Positions Needed for Future Business Plans, and Key Leadership Roles. | MNG, HRD, OPS, EXP, ITE, FBA, GRW, FAC | Company Establishment - Organizational Structure | Company Establishment
|  |  | Develop Future Leaders Launch program to consistently produce strong future leader for the existing and new leaders. | MNG, HRD, EXP | Company Establishment - Talent & Culture | Company Establishment
|  |  | Emergency Fund Optimization Evaluate the company’s current emergency fund strategy and implement the necessary actions to strengthen financial resilience. | MNG, FAC | Company Profitability - Strong Financial and Risk Management | Company Profitability
|  |  | Centralize legal ownership Create a parent company that legally and sufficiently centralize ownership and control of the existing and future businesses. | MNG | Company Establishment - Organizational Structure | Company Establishment
|  |  | Build Finance system Hire and build Financial system and resources for LeadGeeks & Alunara to grow. | MNG, FAC, HRD | Company Profitability - Strong Financial and Risk Management | Company Profitability
|  |  | Perform financial analysis Create financial plan and analysis for both businesses to understand its investment and gain. | FAC, MNG | Company Profitability - Strong Financial and Risk Management | Company Profitability
|  |  | Recruit via Amanda's LinkedIn Promote Amanda LinkedIn account to attract valuable pool of human resources. | MNG, HRD, EXP | Company Establishment - Talent & Culture | Company Establishment
|  |  | Establish central IT team Build IT team that oversees all the technical needs and maintenance of both LeadGeeks & Alunara. | ITE, HRD, MNG, FBA | Company Establishment - Technology Innovation | Company Establishment
|  |  | Right person, right role Continue assessing and putting the right people in the right roles (from internal) as there will be significant changes in the company structure. | MNG, HRD | Company Establishment - Talent & Culture | Company Establishment
|  |  | Launch Circle of Safety Build the training and implementation plan for Circle of Safety creation and extension. | MNG, HRD, EXP | Company Establishment - Talent & Culture | Company Establishment
|  |  | Implement rewards system Implement rewards & recognition system for high valued employees. | HRD, EXP, MNG | Company Establishment - Talent & Culture | Company Establishment
|  |  | Empower company culture Continuous assessment, implementation and empowerment of the company culture and values. | EXP, MNG | Company Establishment - Talent & Culture | Company Establishment
|  |  | Implement PMS Implement Performance Management System (PMS) to ensure that every employee’s work | HRD, MNG, OPS, GRW, EXP, FAC, ITE, FBA | Company Establishment - Talent & Culture | Company Establishment
|  |  | Build unique identity Continue creating and maintaining a unique identity and image for a company in the minds of its employees and the public. | GRW, MNG | Company Establishment - Talent & Culture | Company Establishment

## Company Focus
100% multiplier | Budget spent per $100,000 | in IDR

## Company Focus (2026) (hidden)
Company Priority with ratio for budget, time, & initiatives | Sub Priority with ratio for budget, time, & initiatives | Main PIC | Details | 100% multiplier | Budget spent per $100,000 | in IDR | Impact | Effort | Timeline

## Sheet7 (hidden)
1. Strategic Direction and Enterprise Planning | SG SOP Optimization: 1. Performance Analysis | To find out how well our current rules are working, by reviewing last year’s data and team feedback, in order to identify which parts of the workflow are slow or confusing. | 1. 1 of SOP Evaluation Report (Document) | EA |  | MNG | MNG | Started in 0 month(s) and 14 day(s) | Not started | Not Started | OPS, GRW, EXP, HRD, ITE | Yes | Program | Annual | 1. Complexity Low 2. Frequency Low 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Organizational Structure | 2026-02-02 | 2026-03-27 | Masukan dari Amanda for new leaders: 1. Exposure untuk cara pembuatan SMART Goals saat Onboarding 2. Brainstorming bersama SPV
1. Strategic Direction and Enterprise Planning | SG SOP Optimization: 2. Framework Design | To update our goal-setting and work rules, by refining the existing draft of the SOP based on the evaluation findings, in order to make our processes faster and easier to follow. | 1. 1 of Updated SOP (Document & Canva) | EA |  | MNG | MNG | Started in 2 month(s) and 11 day(s) | Not started | Not Started |  | No |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Organizational Structure | 2026-03-30 | 2026-06-26
1. Strategic Direction and Enterprise Planning | SG SOP Optimization: 3. Socialization | To align the team with the new changes, by holding a socialization to discuss the revisions and gather final input, in order to ensure everyone understands how to use the improved system. | 1. 1 of SOP Revision Socialization (Event) 2. 1 of Feedback List (Document) | EA |  | MNG | MNG | Started in 5 month(s) and 10 day(s) | Not started | Not Started | OPS, GRW, EXP, HRD, ITE, FAC, FBA | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Organizational Structure | 2026-06-29 | 2026-08-28
1. Strategic Direction and Enterprise Planning | SG SOP Optimization: 4. Full Implementation | To activate the improved work standards, by applying the new SOP across all departments for the 2027 cycle, in order to reach higher efficiency and meet our strategic targets. | 1. 1 of New SOP Launch (Event) 2. 1 of Actionable Items List for 2026 cycle (Document) | EA |  | MNG | MNG | Started in 7 month(s) and 12 day(s) | Not started | Not Started | OPS, GRW, EXP, HRD, ITE, FAC, FBA | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Organizational Structure | 2026-08-31 | 2026-12-18
1. Strategic Direction and Enterprise Planning | Annual Financial Objectives | To establish clear and achievable financial targets by conducting thorough financial analysis in order to guide strategic decision-making, optimize resource allocation, and ensure sustainable business growth. | 1. 1 Financial Objective Document consisting the following targets: A. Revenue 1. Total Revenue 2. Revenue (Customer Acquisition) 3. Revenue (Customer Retention) B. Profit 1. Total Profit 2. Profit Margin | MD | Improvement | MNG | MNG | 2 month(s) and 8 day(s) left | Not started | Ongoing | OPS, GRW, EXP, HRD, FAC, ITE, FBA | Yes | Program | Annual | 1. Complexity Mid 2. Frequency Mid 3. Execution Period Mid | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Profitability - Strong Financial and Risk Management | 2026-01-02 | 2026-03-27 | Collaboration is aimed to support MD with: - Reliable financial input for decision-making - Early warning signals before targets are missed - Clear visibility into what is driving or hurting revenue and profit - Confidence that strategy is being executed on the ground
1. Strategic Direction and Enterprise Planning | Succession: 1. Strategy & Leadership Framework | To define the future leadership standard, by identifying the core competencies required for the 2 target management positions and establishing development strategies for potential successors, in order to ensure the next generation of leaders aligns with the Company's vision, mission, and culture. | 1. 1 of Leadership Competency & Development Framework (Document). | MD | Breakthrough | MNG | MNG | Started in 0 month(s) and 14 day(s) | Not started | Not Started | OPS, GRW, EXP, HRD, ITE | Yes | Program | Occasional | 1. Complexity High 2. Frequency Mid 3. Execution Period Mid | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Organizational Structure | 2026-02-02 | 2026-06-30
1. Strategic Direction and Enterprise Planning | Succession: 2. Structural & Resource Planning | To prepare the organization for leadership changes, by approving the new organizational structures and pre-allocating the human/financial resources needed to support the new managers, in order to prevent operational bottlenecks during the transition. | 1. 1 of Org Chart & Resource Allocation Plan | MD | Breakthrough | MNG | MNG | Started in 0 month(s) and 14 day(s) | Not started | Not Started | OPS, GRW, EXP, HRD, ITE | Yes | Program | Occasional | 1. Complexity Mid 2. Frequency Mid 3. Execution Period Short | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Organizational Structure | 2026-02-02 | 2026-06-30
1. Strategic Direction and Enterprise Planning | Succession: 3. Enterprise Risk & Continuity Oversight | To protect the company from transition-related instability, by identifying enterprise risks (e.g., loss of "tribal knowledge," client relationship gaps) and establishing mitigation safeguards, in order to ensure business continuity during the management hand-over. | 1. 1 of Succession Risk Mitigation & Continuity Report | MD | Breakthrough | MNG | MNG | Started in 0 month(s) and 14 day(s) | Not started | Not Started | OPS, GRW, EXP, HRD, ITE | Yes | Program | Occasional | 1. Complexity High 2. Frequency Mid 3. Execution Period Mid | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Organizational Structure | 2026-02-02 | 2026-06-30
1. Strategic Direction and Enterprise Planning | Succession: 4. Training & Review | To execute the Leadership Development Framework, by designing and implementing structured training frameworks and review templates, in order to enable effective onboarding of new successors. | 1. 100% of training sessions delivered to all participants according to the planned timeline 2. 100% of review sessions delivered to all participants according to the planned timeline | MD | Breakthrough | MNG | MNG | Started in 5 month(s) and 12 day(s) | Not started | Not Started | EXP, HRD, ITE, OPS, GRW, FAC, FBA | Yes | Training (Cross-Departmental) | Occasional | 1. Complexity High 2. Frequency High 3. Execution Period Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Talent & Culture | 2026-07-01 | 2026-12-31
1. Strategic Direction and Enterprise Planning | Workforce Planning: 1. Needs Assessment & Role Definition | To identify the ideal leadership profiles, by defining specific roles, responsibilities, and qualifications for 2 managerial positions and submitting a formal request to HRD, in order to ensure new hires meet our growth requirements. | 1. 1 set of Managerial Job Description & Requirement Set | MD | Breakthrough | MNG | MNG | 2 month(s) and 12 day(s) left | Not started | Ongoing | HRD | No | Program | Occasional | 1. Complexity Low 2. Frequency Low 3. Execution Period Short | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Talent & Culture | 2026-01-19 | 2026-03-31
1. Strategic Direction and Enterprise Planning | Workforce Planning: 2. Recruitment Support | To secure top-tier leadership talent, by assisting the HRD in the recruitment process through technical interviews and cultural fit assessments, in order to select the most qualified candidates for the leadership pipeline. | 1. 1 set of Candidate Assessment & Selection Report | MD | Breakthrough | MNG | MNG | Started in 0 month(s) and 14 day(s) | Not started | Not Started | HRD | Yes | Program | Occasional | 1. Complexity Mid 2. Frequency High 3. Execution Period Mid | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Talent & Culture | 2026-02-02 | 2026-03-31
1. Strategic Direction and Enterprise Planning | Workforce Planning: 3. Onboarding Process | To accelerate the productivity of new hires, by creating and implementing a structured onboarding framework that covers company culture, tools, and strategic goals, in order to ensure a smooth transition into their leadership roles. | 1. 2 of Leadership Onboarding Program (Document) | MD | Breakthrough | MNG | MNG | Started in 0 month(s) and 14 day(s) | Not started | Not Started | HRD, EXP, OPS, GRW, FAC, ITE, FBA | Yes | Training (Cross-Departmental) | Occasional | 1. Complexity High 2. Frequency High 3. Execution Period Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Talent & Culture | 2026-02-02 | 2026-06-30
1. Strategic Direction and Enterprise Planning | Workforce Planning: 4. Performance Review | To ensure long-term leadership success, by conducting periodic performance reviews for the new hires during their first 3 and 6 months, in order to assess their integration and provide necessary support for their growth. | 1. 2 of New Hire Periodic Evaluation Logs | MD | Breakthrough | MNG | MNG | Started in 0 month(s) and 13 day(s) | Not started | Not Started | HRD, EXP, GRW, OPS, ITE | Yes | Program | Occasional | 1. Complexity Mid 2. Frequency Low 3. Execution Period Mid | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Talent & Culture | 2026-02-01 | 2026-12-18
2. Advancement and Change Governance | Data Governance: 1. Naming & Entry Standards | To make sure our data is clean and consistent, by creating a simple guide on how to name files, categorize leads, and format dates/numbers, in order to prevent messy data from breaking the system when we move to Cloud System. | 1. 1 of Data Standardization Guide (Document) | EA |  | MNG | MNG | Started in 0 month(s) and 14 day(s) | Not started | Not Started | ITE, OPS | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Technology Innovation | 2026-02-02 | 2026-03-27
2. Advancement and Change Governance | Data Governance: 2. System Mapping | To blueprint how our current files fit together, by mapping out which Google Sheets will turn into which Cloud System tables (e.g., Leads, Clients, Projects), in order to ensure no information is lost during the migration. | 1. 1 of Database System Map (Document/Diagram) | EA |  | MNG | MNG | Started in 2 month(s) and 11 day(s) | Not started | Not Started | ITE, OPS | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Technology Innovation | 2026-03-30 | 2026-12-18
2. Advancement and Change Governance | Data Governance: 3. 2027 Migration Roadmap | To plan the technical transition, by defining clear milestones, a quarterly timeline, and the necessary resources (talent & tools), in order to ensure the 2027 migration is delivered on time and within budget. | 1. 1 of 2027 Migration Strategy (includes Timeline & Resource Plan). | EA |  | MNG | MNG | Started in 5 month(s) and 10 day(s) | Not started | Not Started | ITE, OPS | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Technology Innovation | 2026-06-29 | 2026-12-18
2. Advancement and Change Governance | Invoice System: 1. Structural Redesign | To support complex project billing, by redesigning the Invoice Data to accommodate accrual accounting, cross-fiscal years, and multiple agreements per project , in order to ensure every payment is tracked against its specific contract version. | 1. 1 of Updated Document Template (Document) | EA |  | MNG | MNG | Started in 0 month(s) and 14 day(s) | Not started | Not Started | FAC | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Technology Innovation | 2026-02-02 | 2026-04-24
2. Advancement and Change Governance | Invoice System: 2. AppsScript Automation | To reduce manual follow-up and improve cash flow, by developing an AppsScript reminder system that sends automatic email notifications based on invoice status, in order to standardize the payment collection process without manual intervention. | 1. 1 of Automated Reminder Script & Protocol (System) | EA |  | MNG | MNG | Started in 2 month(s) and 18 day(s) | Not started | Not Started | FAC, ITE | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Technology Innovation | 2026-04-06 | 2026-05-08
2. Advancement and Change Governance | Invoice System: 3. Data Migration & Reconciliation and Performance Monitoring | To transition to the new structured format, by migrating existing billing records into the new data schema and reconciling cross-fiscal year accruals, in order to ensure a clean financial history before fully retiring the old system. | 1. 1 of Completed Invoice Data Migration (Document/Database) | EA |  | MNG | MNG | Started in 3 month(s) and 22 day(s) | Not started | Not Started | FAC | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Technology Innovation | 2026-05-11 | 2026-05-29 | Tambah Performance Monitoring
2. Advancement and Change Governance | Invoice System: 4. Dashboard Update | To re-align our visual reporting with the new database, by updating the Looker Studio data sources and adjusting the existing Recap charts (Incomes per project, month, process, and growth contribution), in order to maintain accurate oversight of agency performance. | 1. 1 of Refined Invoice & Payment Recap Dashboard (System) | EA |  | MNG | MNG | Started in 4 month(s) and 13 day(s) | Not started | Not Started | FAC | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Technology Innovation | 2026-06-01 | 2026-06-26
2. Advancement and Change Governance | Price Calculator: 1. Variable Identification | To list all parts of our pricing, by grouping monthly, result-based, and add-ons costs, in order to build a clear base for different types of services, markets, etc. | 1. 1 of Pricing Variable List (Document) | EA |  | MNG | MNG | Started in 1 month(s) and 11 day(s) | Not started | Not Started | OPS, GRW, HRD, FAC, EXP | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Technology Innovation | 2026-03-02 | 2026-03-27
2. Advancement and Change Governance | Price Calculator: 2. Tool Creation | To build an easy-to-use calculation file, by adding math formulas and price increase settings into a sheet, in order to make sure all quotes are correct. | 1. 1 of Price Calculator Sheet (Document). | EA |  | MNG | MNG | Started in 2 month(s) and 11 day(s) | Not started | Not Started | OPS, GRW, HRD, FAC, EXP | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Technology Innovation | 2026-03-30 | 2026-04-24
2. Advancement and Change Governance | Price Calculator: 3. Tool Socialization | To teach relevant stakeholders how to use the Price Calculator, by holding a short practice meeting for everyone, in order to make sure all staff use the same prices. | 1. 1 of Training Session (Event). | EA |  | MNG | MNG | Started in 3 month(s) and 8 day(s) | Not started | Not Started | OPS, GRW, HRD, FAC, EXP | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Technology Innovation | 2026-04-27 | 2026-05-29
2. Advancement and Change Governance | Price Calculator: 4. Implementation | To start using the new tool for all clients, by sending out all new price offers through the calculator, in order to keep our income steady and fair. | 1. 1 Pricing Backlog (Document) | EA |  | MNG | MNG | Started in 4 month(s) and 13 day(s) | Not started | Not Started | OPS, GRW, HRD, FAC, EXP | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Technology Innovation | 2026-06-01 | 2026-12-18
3. Financial Stewardship and Capital Strategy | 2026 Budget: 1. Resource Needs Analysis | To identify all department spending needs, by designing a simple template for managers to list their required tools, staff, and costs, in order to gather accurate data for the 2026 plan. | 1. 1 of Departmental Budget Submission Template (Document) | EA | Improvement | MNG | MNG | 0 month(s) and 12 day(s) left | Not started | Ongoing | OPS, GRW, EXP, HRD, FAC, ITE, FBA | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Profitability - Strong Financial and Risk Management | 2026-01-02 | 2026-01-31
3. Financial Stewardship and Capital Strategy | 2026 Budget: 2. Master Sheet Design | To build the master financial plan, by combining department cost requests with our 2026 income goals into one sheet, in order to calculate our expected profit and cash flow. | 1. 1 of Master Budget & Financial Projection Sheet (Document) | EA | Improvement | MNG | MNG | Started in 0 month(s) and 13 day(s) | Not started | Not Started |  | No |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Profitability - Strong Financial and Risk Management | 2026-02-01 | 2026-03-27
3. Financial Stewardship and Capital Strategy | 2026 Budget: 3. Executive Review | To match our spending with company goals, by holding a review meeting with the MD and department heads, in order to adjust costs and ensure everyone is working toward the same targets. | 1. 1 of Executive Budget Alignment Meeting (Event) | MD | Improvement | MNG | MNG | 2 month(s) and 12 day(s) left | Not started | Ongoing | OPS, GRW, EXP, HRD, FAC, ITE, FBA | Yes | Program | Annual | 1. Complexity High 2. Frequency Mid 3. Execution Period Mid | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Profitability - Strong Financial and Risk Management | 2026-01-02 | 2026-03-31
3. Financial Stewardship and Capital Strategy | 2026 Budget: 4. Final Approval | To secure the official company budget, by getting the final sign-off from the MD on the 2026 numbers, in order to give the team the green light to start spending within their limits. | 1. 1 of Approved 2026 Annual Budget (Document) | MD | Improvement | MNG | MNG | 2 month(s) and 12 day(s) left | Not started | Ongoing | FAC | Yes | Program | Annual | 1. Complexity High 2. Frequency High 3. Execution Period Mid | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Profitability - Strong Financial and Risk Management | 2026-01-02 | 2026-03-31
3. Financial Stewardship and Capital Strategy | FBA Bonus System: 1. Factors Identification | To identify key performance indicators, by analyzing operational milestones, in order to establish a fair baseline for first-year rewards. | 1. 1 document of Approved Bonus Factor List | MD |  | MNG | MNG | Started in 0 month(s) and 14 day(s) | Not started | Not Started | HRD, FAC | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Profitability - Strong Financial and Risk Management | 2026-02-02 | 2026-03-27
3. Financial Stewardship and Capital Strategy | FBA Bonus System: 2. Workflow Design | To design a structured bonus workflow, by mapping internal approval steps, in order to ensure transparent and timely payouts. | 1. 1 document of FBA Bonus System Workflow | MD |  | MNG | MNG | Started in 2 month(s) and 18 day(s) | Not started | Not Started | HRD, FAC | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Profitability - Strong Financial and Risk Management | 2026-04-06 | 2026-06-26
3. Financial Stewardship and Capital Strategy | FBA Bonus System: 3. Review | To validate the incentive framework, by auditing budget availability and payout fairness, in order to ensure financial sustainability and team equity. | 1. 1 document of Review Meeting Report | MD |  | MNG | MNG | Started in 2 month(s) and 18 day(s) | Not started | Not Started | HRD, FAC | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Profitability - Strong Financial and Risk Management | 2026-04-06 | 2026-06-26
3. Financial Stewardship and Capital Strategy | FBA Bonus System: 4. Implementation | To launch the FBA bonus system, by formally presenting terms to the team and implementing the bonus system accordingly, in order to drive high performance and employee retention. | 1. 1 event of Bonus System Team Socialization 2. 1 Bonus Tracking Document for Transparent Calculation and Approval | MD |  | MNG | MNG | Started in 5 month(s) and 17 day(s) | Not started | Not Started | HRD, FAC | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Profitability - Strong Financial and Risk Management | 2026-07-06 | 2026-12-18
4. Executive Leadership and Organizational Culture | Leadership Camp: 1. Program Ideation | To initiate the Leadership Camp program by defining clear purpose, outcomes, success criteria, theme, and high-level program structure, in order to ensure the Leadership Camp is aligned, outcome-driven, and execution-ready. | 1. 1 Leadership Camp Purpose & Success Metrics (Document) 2. 1 Leadership Camp Theme (Document) 3. 1 High-Level Program Structure & Agenda Flow (Document) 4. 1 approved Leadership Camp Committee List (Document) 5. 1 approved High-Level Budget (Document) | MD | Improvement | MNG | MNG, EXP | Started in 1 month(s) and 11 day(s) | Not started | Not Started | EXP, FAC | Yes | Program | Annual | 1. Complexity High 2. Frequency Mid 3. Execution Period Mid | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Talent & Culture | 2026-03-02 | 2026-04-30
4. Executive Leadership and Organizational Culture | Leadership Camp: 2. Program Preparation | To develop a detailed Leadership Camp program and materials, by translating the approved theme and leadership outcomes into structured sessions, activities, and facilitation materials, in order to enable effective delivery and consistent leadership learning experiences. | 1. 1 Approved Detailed Leadership Camp Program (Document) 2. 100% Materials Approved by Program PIC 3. 100% Briefing Sessions with Participants | MD | Improvement | MNG | MNG, EXP | Started in 3 month(s) and 12 day(s) | Not started | Not Started | EXP, GRW, OPS, HRD, ITE | Yes | Program | Annual | 1. Complexity High 2. Frequency High 3. Execution Period Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Talent & Culture | 2026-05-01 | 2026-07-31
4. Executive Leadership and Organizational Culture | Leadership Camp: 3. Program Execution | To execute the Leadership Camp program as planned, by delivering all approved sessions according to the defined agenda, coordinating facilitators and logistics, and ensuring active participant engagement throughout the program, in order to achieve the intended leadership learning outcomes and ensure consistent, high-quality program delivery. | 1. 100% of Leadership Camp sessions delivered in accordance with the approved program and timeline 2. 100% facilitator and logistics readiness confirmed prior to execution (venue, tools, materials, run-of-show) 3. ≥90% participant attendance rate across all scheduled sessions | MD | Improvement | MNG | MNG, EXP | Started in 6 month(s) and 15 day(s) | Not started | Not Started | EXP, GRW, OPS, HRD, ITE, FAC, FBA | Yes | Program | Annual | 1. Complexity High 2. Frequency Mid 3. Execution Period Mid | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Talent & Culture | 2026-08-03 | 2026-10-30
4. Executive Leadership and Organizational Culture | Leadership Camp: 4. Program Review & Evaluation | To evaluate Leadership Camp program effectiveness and define follow-up actions, by collecting feedback, assessing leadership behavior signals, and documenting lessons learned, in order to reinforce leadership development, improve future programs, and drive sustained leadership impact. | 1. 1 Leadership Camp Evaluation Report 2. 1 Participant Feedback Report collected from 100% participants 3. 80% Achievement of Success Metrics | MD | Improvement | MNG | MNG, EXP | Started in 9 month(s) and 14 day(s) | Not started | Not Started | EXP, GRW, OPS, HRD, ITE, FAC, FBA | Yes | Program | Annual | 1. Complexity Mid 2. Frequency Low 3. Execution Period Short | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Talent & Culture | 2026-11-02 | 2026-11-27
5. Governance, Risk, and Compliance Oversight | Non-Disclosure Agreement (NDA): 1. Revision & Review | To finalize the confidentiality framework, by revising existing terms and conducting a final review with key stakeholders, in order to ensure all proprietary interests are protected. | 1. 1 of Final NDA Draft | EA |  | MNG | MNG | Started in 0 month(s) and 14 day(s) | Not started | Not Started | HRD | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Organizational Structure | 2026-02-02 | 2026-06-26
5. Governance, Risk, and Compliance Oversight | Non-Disclosure Agreement (NDA): 2. Approval & Socialization | To implement the new confidentiality standard, by securing MD approval and socializing the terms with employees, in order to ensure company-wide legal compliance. | 1. 1 of Approved NDA 2. Socialization Record | EA |  | MNG | MNG | Started in 5 month(s) and 17 day(s) | Not started | Not Started | OPS, GRW, EXP, HRD, FAC, ITE | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Organizational Structure | 2026-07-06 | 2026-12-18 | Tanda tangan tambahan tugas HRD
5. Governance, Risk, and Compliance Oversight | Service Agreement: 1. Internal Audit & Requirements Mapping | To identify internal operational and legal concerns, by internally auditing current templates for gaps in multi-national jurisdiction (US/EU/ID), IP rights, data protection, and other topics, in order to create a comprehensive list of requirements for legal consultation. | 1. 1 of Internal Legal Requirements & Gap Report | EA |  | MNG | MNG | Started in 0 month(s) and 14 day(s) | Not started | Not Started | OPS, GRW, EXP, HRD, FAC, ITE | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Organizational Structure | 2026-02-02 | 2026-06-26
5. Governance, Risk, and Compliance Oversight | Service Agreement: 2. Attorney Consultation & Strategic Refinement | To resolve cross-border and operational legal risks, by consulting with an attorney on the internal requirements list and drafting revised clauses for jurisdiction, pricing impacts (work hours/leave), and liability, in order to produce a legally sound and operationally protected contract draft. | 1. 1 of Revised Service Agreement Master Template (Document) | EA |  | MNG | MNG | Started in 5 month(s) and 10 day(s) | Not started | Not Started | OPS, GRW, EXP, HRD, FAC, ITE | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Organizational Structure | 2026-06-29 | 2026-09-25
5. Governance, Risk, and Compliance Oversight | Service Agreement: 3. Validation & Socialization | To activate the operational framework, by obtaining final attorney validation and MD approval followed by team socialization, in order to arm the company team with the updated contract. | 1. 1 of Validated Service Agreement 2. Leaders Briefing Session | EA |  | MNG | MNG | Started in 8 month(s) and 16 day(s) | Not started | Not Started | OPS, GRW, EXP, HRD, FAC, ITE | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Organizational Structure | 2026-10-05 | 2026-11-27
5. Governance, Risk, and Compliance Oversight | GDPR Practice Compliance: 1. Operational Audit | To verify lead generation and outbound marketing legality, by reviewing scraping, outbound marketing, and storage practices in the EU market, in order to identify potential privacy violations. | 1. 1 of Practice Compliance Audit | EA |  | MNG | MNG | Started in 0 month(s) and 14 day(s) | Not started | Not Started | OPS, GRW, EXP, ITE, HRD | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Organizational Structure | 2026-02-02 | 2026-06-26
5. Governance, Risk, and Compliance Oversight | GDPR Practice Compliance: 2. Audit Reporting | To brief leadership team on practices compliance, by presenting the audit findings and high-risk gaps to internal key stakeholders, in order to enable executive decisions on market-specific risk tolerance. | 1. 1 of Internal GDPR Compliance Executive Report | EA |  | MNG | MNG | Started in 5 month(s) and 17 day(s) | Not started | Not Started | OPS, GRW, EXP, ITE, HRD | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Organizational Structure | 2026-07-06 | 2026-09-25
5. Governance, Risk, and Compliance Oversight | GDPR Standard Contractual Clauses (SCC): 1. Consultation & Mapping | To structure legal data transfers, by consulting with an attorney on rights/responsibilities regarding Standard Contractual Clauses, in order to map out the legal bridge between Indonesia and the EU. | 1. 1 of SCC Legal Consultation Brief 2. 1 of SCC Legal Consultation Report | EA |  | MNG | MNG | Started in 0 month(s) and 14 day(s) | Not started | Not Started | OPS, GRW, EXP, ITE, HRD | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Organizational Structure | 2026-02-02 | 2026-06-26
5. Governance, Risk, and Compliance Oversight | GDPR Standard Contractual Clauses (SCC): 2. Template Creation & Review | To standardize data agreements, by creating an SCC template followed by a final legal review, in order to enable compliant data processing for EU projects. | 1. 1 of Approved SCC Template | EA |  | MNG | MNG | Started in 5 month(s) and 17 day(s) | Not started | Not Started | OPS, GRW, EXP, ITE, HRD | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Organizational Structure | 2026-07-06 | 2026-09-25
5. Governance, Risk, and Compliance Oversight | GDPR Standard Contractual Clauses (SCC): 3. Socialization | To ensure team awareness, by conducting a socialization session on the role of SCCs in our operations, in order to prevent accidental compliance breaches. | 1. 1 Leaders Briefing Session | EA |  | MNG | MNG | Started in 8 month(s) and 16 day(s) | Not started | Not Started | OPS, GRW, EXP, ITE, HRD | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Organizational Structure | 2026-10-05 | 2026-11-27
5. Governance, Risk, and Compliance Oversight | Brand Registration: 1. Brand Protection Consultation | To assess our IP standing, by consulting with legal experts on trademark compliance and registration risks, in order to understand the necessary steps for brand security. | 1. 1 of IP Consultation Summary | EA |  | MNG | MNG | Started in 0 month(s) and 14 day(s) | Not started | Not Started |  | No |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Organizational Structure | 2026-02-02 | 2026-06-26
5. Governance, Risk, and Compliance Oversight | Brand Registration: 2. Strategy | To finalize the protection roadmap, by documenting follow-up actions and risk-mitigation steps, in order to secure the LeadGeeks brand in all active markets. | 1. 1 of Brand Registration Strategy Report | EA |  | MNG | MNG | Started in 5 month(s) and 17 day(s) | Not started | Not Started | GRW | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Organizational Structure | 2026-07-06 | 2026-11-27
6. Enterprise Operations Oversight | SOP: 1. Review & Feedback | To ensure new procedures are efficient and safe, by reviewing incoming SOP requests from other departments for clarity, operational risks, and cross-departmental friction, and giving final approval for implementation, in order to provide feedback for refinement before finalization. | 1. 1 of SOP Review Feedback Log Showing 100% Request is Reviewed (Document) | EA |  | MNG | MNG | 10 month(s) and 8 day(s) left | Not started | Ongoing | OPS, GRW, EXP, HRD, FAC, ITE | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Organizational Structure | 2026-01-02 | 2026-11-27
6. Enterprise Operations Oversight | Growth Dept: 1. Structure & Role Approval | To optimize the Growth team design, by approving the reporting lines AND the specific "Job Descriptions" (JDs) for each niche role, in order to ensure every position has a clear, measurable output that contributes to company revenue. | 1. 1 of Approved Growth Org Chart & Role Definitions (Document) | MD | Breakthrough | MNG | MNG | Started in 0 month(s) and 14 day(s) | Not started | Not Started | GRW, HRD | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Organizational Structure | 2026-02-02 | 2026-11-27
6. Enterprise Operations Oversight | Growth Dept: 2. Cross-Departmental Resource Allocation | To ensure Growth activities support the whole company, by assessing and approving the Growth Dept’s plan for resource delegation to verify they align with the visions of other departments, in order to guarantee that new business wins are manageable. | 1. 1 of Growth-to-Enterprise Alignment Map (Document) | MD | Breakthrough | MNG | MNG | Started in 0 month(s) and 14 day(s) | Not started | Not Started | GRW, HRD | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Organizational Structure | 2026-02-02 | 2026-11-27
6. Enterprise Operations Oversight | Growth Dept: 3. Operational Risk & Performance Oversight | To assist the Growth Dept in identifying enterprise-level risks, by reviewing their operational risk assessments and providing executive guidance on mitigation, in order to ensure the department’s expansion doesn't create unforeseen operations or financial liabilities. | 1. 1 of Growth Risk Oversight Summary (Document) | MD | Breakthrough | MNG | MNG | Started in 0 month(s) and 14 day(s) | Not started | Not Started | GRW, HRD | Yes | Program | Occasional | 1. Complexity High 2. Frequency High 3. Execution Period Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Organizational Structure | 2026-02-02 | 2026-06-30
6. Enterprise Operations Oversight | PMS: 1. KPI Submission & Coordination | To initiate the goal-setting cycle, by requesting and overseeing the annual KPI submission process for Managing Director and all of her supervisees, in order to ensure every department head has documented their proposed targets and success metrics for the year. | 1. 1 of KPI Submission Log | MD |  | MNG | MNG | Started in 0 month(s) and 14 day(s) | Not started | Not Started | HRD, OPS, GRW, EXP, FAC, ITE | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Organizational Structure | 2026-02-02 | 2026-02-13
6. Enterprise Operations Oversight | PMS: 2. KPI Strategic Review & Approval | To ensure goal alignment, by performing a detailed review of all KPI proposals and granting final approval, in order to verify that individual targets support the company's 2026 strategic niche and revenue goals. | 1. 1 of Approved Master KPI Document | MD |  | MNG | MNG | Started in 0 month(s) and 28 day(s) | Not started | Not Started | HRD | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Organizational Structure | 2026-02-16 | 2026-03-27
6. Enterprise Operations Oversight | PMS: 3. Monthly Task Assignment | To guide short-term execution, by formally assigning monthly tasks and projects to supervisees, in order to ensure the high-level KPIs are broken down into actionable, manageable steps. | 1. 12 of Monthly Task Assignment Records | EA |  | MNG | MNG | Started in 1 month(s) and 11 day(s) | Not started | Not Started | HRD | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Organizational Structure | 2026-03-02 | 2026-11-30
6. Enterprise Operations Oversight | PMS: 4. Half-Year Performance Evaluation | To assess mid-point progress, by conducting a formal half-year performance evaluation for each supervisee based on accumulated PMS data, in order to adjust targets or provide intensive coaching where necessary. | 1. 1 of Consolidated Half-Year Evaluation Report | MD |  | MNG | MNG | Started in 5 month(s) and 17 day(s) | Not started | Not Started | HRD, OPS, GRW, EXP, FAC, ITE | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Organizational Structure | 2026-07-06 | 2026-08-28
6. Enterprise Operations Oversight | PMS: 5. Program Evaluation & Optimization | To improve the management toolset, by evaluating the overall PMS program’s effectiveness at year-end, in order to identify gaps in the process and refine the system for the 2027 management transition. | 1. 1 of PMS Program Evaluation Report | MD |  | MNG | MNG | Started in 10 month(s) and 18 day(s) | Not started | Not Started | HRD, OPS, GRW, EXP, FAC, ITE | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Organizational Structure | 2026-12-07 | 2026-12-18
8. Stakeholder and Ecosystem Engagement | Brand Strategy: 1. Positioning & Strategy Review and Approval | To authorize the company's market identity, by assessing and approving the Growth Department’s marketing goals, channel segmentation, and brand positioning & messaging, in order to ensure a consistent and high-authority brand voice across all public-facing platforms. | 1. 1 of Approved Strategic Brand Framework (Document) | EA |  | MNG | MNG | Started in 0 month(s) and 14 day(s) | Not started | Not Started | GRW | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Branding, Communication & Experience | 2026-02-02 | 2026-06-26
8. Stakeholder and Ecosystem Engagement | Amanda’s LinkedIn: 1. Strategy & Objective Setting | To establish the foundation for Amanda’s LinkedIn presence, by defining clear communication goals and her unique content pillars, in order to align her personal voice with LeadGeeks’ 2026 strategic vision. | 1. 1 of Approved Branding Brief (Document) | EA |  | MNG | MNG | Started in 0 month(s) and 14 day(s) | Not started | Not Started | GRW | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Branding, Communication & Experience | 2026-02-02 | 2026-03-27
8. Stakeholder and Ecosystem Engagement | Amanda’s LinkedIn: 2. Planning & Implementation | To maintain a consistent high-authority presence, by approving a monthly content calendar and overseeing the publishing of thought-leadership posts and industry commentary, in order to increase profile visibility among key niche stakeholders. | 1. 1 of Active Content Calendar & Posting Schedule | EA |  | MNG | MNG | Started in 0 month(s) and 14 day(s) | Not started | Not Started | GRW | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Branding, Communication & Experience | 2026-02-02 | 2026-11-27
8. Stakeholder and Ecosystem Engagement | Amanda’s LinkedIn: 3. Evaluation & Optimization | To measure the impact of the branding efforts, by analyzing profile growth and the quality of new connections, in order to improve the content to better support business goals. | 1. 1 of Quarterly LinkedIn Impact Report | EA |  | MNG | MNG | Started in 2 month(s) and 18 day(s) | Not started | Not Started | GRW | Yes |  |  | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Branding, Communication & Experience | 2026-04-06 | 2026-11-27

## MNG_Corat Coret (hidden)
Department Functions | Department Goals | For Prioritization Purposes | No. | Department Goals (Specific) | Indicators (Measurable) | Day Counter | Status | Date of Accomplishment | Accomplishment Status | Goals Type | Owner | PIC | Collaborators | Collaboration | Type | Period | Expectations for Collaborators | Strengths | Weaknesses | Opportunities | Threats | Resources Availability (Attainable) | Resources Invailability (Attainable) | Company Goals Reference (Relevance) | Start date (Time bound) | End date (Time bound) | Notes | Half Adjustment | Updated Goal_Initial | Updated Goal_Reason | Updated Specific_Initial | Updated Specific_Reason | Updated Measurable_Initial | Updated Measurable_Reason | Updated Attainable_Initial | Updated Attainable_Reason | Updated Relevant_Initial | Updated Relevant_Reason | Updated Time-Bound_Initial_Start | Updated Time-Bound_Initial_End | Updated Time-Bound_Reason | Additional Note | Indicators Achievement January | Result (Link) January | Challenge January | Homework January | Indicators Achievement February | Result (Link) February | Challenge February | Homework February | Indicators Achievement March | Result (Link) March | Challenge March | Homework March | Indicators Achievement April | Result (Link) April | Challenge April | Homework April | Indicators Achievement May | Result (Link) May | Challenge May | Homework May | Indicators Achievement June | Result (Link) June | Challenge June | Homework June | Indicators Achievement July | Result (Link) July | Challenge July | Homework July | Indicators Achievement August | Result (Link) August | Challenge August | Homework August | Indicators Achievement September | Result (Link) September | Challenge September | Homework September | Indicators Achievement October | Result (Link) October | Challenge October | Homework October | Indicators Achievement November | Result (Link) November | Challenge November | Homework November | Indicators Achievement December | Result (Link) December | Challenge December | Homework December | Internal PIC
ROW FOR ARRAYFORMULA ¦¦ DO NOT CHANGE
Price calculator.. untuk setiap result based, yearly increase (if possible), untuk setiap service, etc
1. Strategic Direction and Enterprise Planning | Price Calculator: Variable Identification |  | 1 | To list all parts of our pricing, by grouping monthly, result-based, and add-ons costs, in order to build a clear base for the calculator. | 1. 1 of Pricing Variable List (Document) | Overdue by 8 month(s) and 14 day(s) |  | 2025-12-02 | Completed: Early | [7 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: - |  | 2025-12-01 | 2025-12-31
1. Strategic Direction and Enterprise Planning | Price Calculator: Tool Creation |  | 2 | To build an easy-to-use calculation file, by adding math formulas and price increase settings into a sheet, in order to make sure all quotes are correct. | 1. 1 of Price Calculator Sheet (Document). | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
1. Strategic Direction and Enterprise Planning | Price Calculator: Tool Socialization |  | 3 | To teach relevant stakeholders how to use the Price Calculator, by holding a short practice meeting for everyone, in order to make sure all staff use the same prices. | 1. 1 of Training Session (Event). | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
1. Strategic Direction and Enterprise Planning | Price Calculator: Implementation |  | 4 | To start using the new tool for all clients, by sending out all new price offers through the calculator, in order to keep our income steady and fair. | 1. 1 Pricing Backlog (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
Business Development coaching for MD (ini juga berangkat dari hasil employee satisfaction form)
4. Executive Leadership and Organizational Culture | Business Development Coaching: Analysis & Survey |  | 1 | To find the best coaching program, by surveying courses that match our team's needs and employee feedback, in order to improve the Managing Director's business skills. | 1. 1 of Coaching Needs Report (Document) 2. 1 of Chosen Course Program (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue | [7 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
4. Executive Leadership and Organizational Culture | Business Development Coaching: Enrollment |  | 2 | To secure a spot in the chosen program, by completing the registration and payment for the selected course, in order to start the professional growth process on time. | 1. 1 of Course Registration Receipt (Document). | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
4. Executive Leadership and Organizational Culture | Business Development Coaching: Training |  | 3 | To complete the learning sessions, by attending all scheduled classes and coaching meetings, in order to gain new skills for growing the company. | 1. 1 of Training Attendance Record (Event). | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
4. Executive Leadership and Organizational Culture | Business Development Coaching: Action Plan |  | 4 | To apply what was learned, by writing a summary and a plan for the company, in order to improve employee satisfaction and business results. | 1. 1 of Business Development Action Plan (Document). | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
|  |  |  | Build Finance System: Setting financial key metrics & goals | [12 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
| Financial Objectives |  |  | To establish clear and achievable financial targets by conducting thorough financial analysis in order to guide strategic decision-making, optimize resource allocation, and ensure sustainable business growth. | 1 target for A. Revenue 1. Total Revenue 2. Revenue (Customer Acquisition) 3. Revenue (Customer Retention) B. Profit 1. Total Profit 2. Profit Margin C. Cost-Benefit Ratio 1. CBR (per Business Model) 2. CBR (per ISR Project) D. Emergency Fund E. Investment
|  |  |  | Tentang struktur dan administratif LeadGeeks Inc jalan (sistem penggajian, sistem budgeting & financial transaction, sistem invoice dari sana kesini, etc) | [12 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
3. Financial Stewardship and Capital Strategy | Budgeting System: Problem & Need Analysis |  | 1 | To evaluate our total spending needs, by reviewing operational costs, growth investments, and financial safety margins, in order to create a complete 12-month budget roadmap. |  | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
3. Financial Stewardship and Capital Strategy | Budgeting System: Design & Framework |  | 2 | To construct a comprehensive budget model, by linking operational spending, investment goals, and cash reserves into one file, in order to give the MD a full view of company spending power. | 1. 1 of Master Budget Sheet (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
3. Financial Stewardship and Capital Strategy | Budgeting System: Forecast Trial |  | 3 | To test the budget's flexibility, by inputting planned expenses and simulating different revenue scenarios, in order to ensure the sheet accurately reflects remaining balances and reserves. | 1. 1 of Budget Simulation Report (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
3. Financial Stewardship and Capital Strategy | Budgeting System: Strategy & Buffer Review |  | 4 | To verify the company’s spending plan, by presenting the full 12-month budget and safety reserves to the MD, in order to align all department spending with company goals. | 1. 1 of Approved Annual Budget (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
3. Financial Stewardship and Capital Strategy | Budgeting System: Implementation & Launch |  | 5 | To activate the new budget limits, by formally sharing department spending goals with all managers, in order to enforce financial discipline across the entire company. | 1. 1 of Budget Rollout Meeting (Event) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
3. Financial Stewardship and Capital Strategy | Budgeting System: Variance Evaluation |  | 6 | To assess budget discipline, by comparing actual spending against the 12-month plan, in order to adjust future allocations and risk buffers. | 1. 1 of Budget Variance Analysis (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
3. Financial Stewardship and Capital Strategy | Financial Transaction System: Problem & Need Analysis |  | 1 | To audit our accrual accounting flow, by tracking how BCA, Jenius, and reimbursement dates are currently recorded, in order to ensure every expense is logged when it occurs. | 1 of Transaction Date Analysis (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
3. Financial Stewardship and Capital Strategy | Financial Transaction System: Design & Framework |  | 2 | To design a multi-source accrual ledger, by creating entry columns for BCA, Jenius, and reimbursements with separate service and payment dates, in order to sync all spending sources. | 1. 1 of Integrated Transaction Ledger (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
3. Financial Stewardship and Capital Strategy | Financial Transaction System: Accrual Trial |  | 3 | To test the multi-source recording, by inputting sample BCA, Jenius, and reimbursement receipts from various months, in order to ensure the accrual dates and cash balances match. | 1. 1 of Transaction Posting Trial (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
3. Financial Stewardship and Capital Strategy | Financial Transaction System: Accrual Process Review |  | 4 | To confirm the new transaction rules, by demonstrating the "Two-Date" recording method for BCA and Jenius to the MD, in order to secure agreement on our bookkeeping standards. | 1. 1 of Bookkeeping Standard Review (Event) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
3. Financial Stewardship and Capital Strategy | Financial Transaction System: Implementation & Launch |  | 5 | To roll out the multi-source ledger, by training cardholders to record BCA, Jenius, and reimbursement data daily, in order to maintain a real-time accrual-based record. | 1. 1 of New Ledger System Kick-off (Event) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
3. Financial Stewardship and Capital Strategy | Financial Transaction System: Accrual Evaluation |  | 6 | To check the "Two-Date" recording system, by reconciling BCA, Jenius, and reimbursement entries against bank statements, in order to ensure 100% match between records and cash. | 1. 1 of Transaction Reconciliation Report (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
3. Financial Stewardship and Capital Strategy | Invoice System: Problem & Need Analysis |  | 1 | To analyze our billing and collection speed, by reviewing late payments and the lack of reminder alerts, in order to identify the main causes of overdue debts. | 1. 1 of Invoicing & Aging Report (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
3. Financial Stewardship and Capital Strategy | Invoice System: Design & Framework |  | 2 | To build an automated billing tracker, by adding conditional formatting for overdue alerts and a standardized reminder schedule, in order to track every client debt in real-time. | 1. 1 of Master Invoice Tracker (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
3. Financial Stewardship and Capital Strategy | Invoice System: Alert & Reminder Trial |  | 3 | To test the overdue tracking, by creating mock invoices with past-due dates, in order to ensure the visual alerts and reminder notifications trigger correctly. | 1. 1 of Invoice Reminder Test Log (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
3. Financial Stewardship and Capital Strategy | Invoice System: Collection & Policy Review |  | 4 | To set the rules for late payments, by deciding on the timing of reminders and legal escalation with the MD, in order to standardize how we handle overdue clients. | 1. 1 of Debt Collection Policy (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
3. Financial Stewardship and Capital Strategy | Invoice System: Implementation & Launch |  | 5 | To activate the smart billing tracker, by moving all active client data into the system and starting the reminder schedule, in order to systematically reduce overdue debts. | 1. 1 of Official Billing Cycle Launch (Event) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
3. Financial Stewardship and Capital Strategy | Invoice System: Collection Evaluation |  | 6 | To measure collection success, by tracking the reduction in "Overdue" days compared to the old system, in order to verify that the reminder alerts are working. | 1. 1 of Collection Performance Report (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
3. Financial Stewardship and Capital Strategy | Payroll System: Problem & Need Analysis |  | 1 | To identify gaps in our salary process, by mapping every step from attendance data to PPh 21 tax filing, in order to standardize monthly pay approvals. | 1. 1 of Payroll Process Audit (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
3. Financial Stewardship and Capital Strategy | Payroll System: Design & Framework |  | 2 | To design a centralized payroll tool, by building a master sheet with PPh 21 formulas and an approval status tracker, in order to automate salary calculations and sign-offs. | 1. 1 of Master Payroll Sheet (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
3. Financial Stewardship and Capital Strategy | Payroll System: System Trial |  | 3 | To test the payroll math and flow, by running a mock pay cycle for different staff categories and tax statuses, in order to verify that PPh 21 and net pay are correct. | 1. 1 of Payroll Trial Result (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
3. Financial Stewardship and Capital Strategy | Payroll System: Policy & Authority Review |  | 4 | To finalize the payroll approval rules, by reviewing staff salary levels and PPh 21 accuracy with the MD, in order to confirm who has the final authority to release pay. | 1. 1 of Payroll Approval Protocol (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
3. Financial Stewardship and Capital Strategy | Payroll System: Implementation & Launch |  | 5 | To start the new payroll routine, by training the team on the salary submission and approval steps, in order to run the first official pay cycle using the new file. | 1. 1 of Live Payroll Run (Event) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
3. Financial Stewardship and Capital Strategy | Payroll System: Process Evaluation |  | 6 | To measure payroll efficiency, by comparing the time taken for salary approvals and payment against previous months, in order to confirm the new system is faster and error-free. | 1, 1 of Payroll Accuracy Report (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
3. Financial Stewardship and Capital Strategy | Tax System: Problem & Need Analysis |  | 1 | To assess our tax filing accuracy, by checking the documentation for PPh 21, 23, and 26 against recent transactions, in order to prevent errors in monthly tax reports. | 1. 1 of Tax Compliance Gap Analysis (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
3. Financial Stewardship and Capital Strategy | Tax System: Design & Framework |  | 2 | To create a tax reporting framework, by linking transaction data to PPh 21, 23, and 26 summary tables, in order to generate accurate tax filing data automatically. | 1. 1 of Tax Summary Dashboard (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
3. Financial Stewardship and Capital Strategy | Tax System: Data Integration Trial |  | 3 | To test the tax summary logic, by linking trial transactions to the tax dashboard, in order to verify that PPh 23 and 26 amounts are captured for filing. | 1. 1 of Tax Calculation Validation (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
3. Financial Stewardship and Capital Strategy | Tax System: Compliance & Filing Review |  | 4 | To ensure tax safety, by checking the PPh 23 and 26 summary logic with management, in order to confirm that all filings will follow Indonesian tax regulations. | 1. 1 of Tax Compliance Sign-off (Event) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
3. Financial Stewardship and Capital Strategy | Tax System: Implementation & Launch |  | 5 | To launch the integrated tax reporting, by using the automated summary dashboard to prepare the monthly filings, in order to ensure 100% compliance with PPh regulations. | 1. 1 of First Automated Tax Summary (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
3. Financial Stewardship and Capital Strategy | Tax System: Compliance Evaluation |  | 6 | To review tax filing speed, by checking if the automated summaries match the final government filings, in order to ensure the system is ready for a full tax year. | 1. 1 of Tax Filing Audit (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
Operating agreement (shared goals with MNG)
5. Governance, Risk, and Compliance Oversight | Multi-Jurisdictional Operating Agreement |  | 1 | To design a multi-jurisdictional operating agreement framework, by conducting legal consultations to define the governance and capital flow between the PT and US entities, in order to establish a legally compliant and scalable foundation for the Alunara LLC subsidiary launch. | 1. 1 Legal Advice Document Key consultation areas: Since you are dealing with a US LLC parent and an Indonesian PT, you need to ask your consultant about: 1. Inter-company Ownership & PMA Rules Since a US LLC will own an Indonesian PT, the PT must be converted into or established as a PT PMA (Foreign Investment Company). a. Does our specific business classification (KBLI) allow for 100% foreign ownership by a US LLC? b. What is the minimum capital requirement ($10$ billion IDR is standard) and how much must be "paid-up" upfront? c. How does the British co-founder's Green Card status affect the US LLC's standing as a foreign investor in Indonesia? d. What are the reporting requirements (LKPM) for a PT owned by a US parent company? e. Can the US Parent LLC provide "Shareholder Loans" to the PT instead of just equity capital? 2. Transfer Pricing & Profit Repatriation You need to move money between Alunara LLC (E-commerce) and the PT without the tax authorities seeing it as tax evasion. a. What is the most tax-efficient "Inter-company Agreement" for Alunara LLC to pay the PT for services? b. How do we set "Arm’s Length" pricing to satisfy both the IRS (US) and DJP (Indonesia) transfer pricing rules? c. What is the withholding tax rate on dividends sent from the PT to the US LLC under the Indonesia-US Tax Treaty? d. If the South African-based founder receives a distribution, how do we handle the "tri-border" tax implication (US-Indo-SA)? e. Can we use "Management Fees" instead of "Dividends" to repatriate profit, and what are the PPh 26 implications? 3. Management Rights & Governance With founders in three different time zones/countries, the Operating Agreement must be airtight regarding "Power of Attorney." a. How do we legally authorize the Managing Director in Indonesia to sign for the US LLC when needed? b. Does the Indonesian Managing Director need a specific "Working Permit" (KITAS) if they are a shareholder in the parent company? c. How can we structure "Digital Signatures" and "Virtual Meetings" in the Operating Agreement to be legally binding in all three countries? d. What "Reserved Matters" (major decisions) must require a unanimous vote vs. a simple majority by the Managing Director? e. How do we handle a "Deadlock" in decision-making if the three partners are geographically and legally separated? 4. Tax Domicile & Residency (The "Residency Trap") This is the highest risk area given the British-US Green Card holder and the South African-based Indonesian. a. Will the US LLC be "Transparent" (Pass-through) or "Opaque" (C-Corp) for tax purposes, and how does that affect the UK/Indonesian partners? b. Does the South African-based partner risk becoming a South African tax resident on their global income from the US/Indo entities? c. As a Green Card holder, how does the British co-founder manage "Substantial Presence" tax rules while operating a global business? d. How do we avoid "Permanent Establishment" (PE) status for the US LLC in Indonesia (which would allow Indonesia to tax the US entity’s profits)? e. Which country's laws should be the "Choice of Law" for the Operating Agreement (e.g., Delaware Law vs. Indonesian Law)? | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue | [7 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
Create budget & planning 2026
3. Financial Stewardship and Capital Strategy | 2026 Budget: Resource Needs Analysis |  | 1 | To identify all department spending needs, by designing a simple template for managers to list their required tools, staff, and costs, in order to gather accurate data for the 2026 plan. | 1. 1 of Departmental Budget Submission Template (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue | [7 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
3. Financial Stewardship and Capital Strategy | 2026 Budget: Master Sheet Design |  | 2 | To build the master financial plan, by combining department cost requests with our 2026 income goals into one sheet, in order to calculate our expected profit and cash flow. | 1. 1 of Master Budget & Financial Projection Sheet (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
3. Financial Stewardship and Capital Strategy | 2026 Budget: Executive Review |  | 3 | To match our spending with company goals, by holding a review meeting with the MD and department heads, in order to adjust costs and ensure everyone is working toward the same targets. | 1. 1 of Executive Budget Alignment Meeting (Event) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
3. Financial Stewardship and Capital Strategy | 2026 Budget: Final Approval |  | 4 | To secure the official company budget, by getting the final sign-off from the MD on the 2026 numbers, in order to give the team the green light to start spending within their limits. | 1. 1 of Approved 2026 Annual Budget (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
Revisi SOP, flow, etc SMART Goals processes
6. Enterprise Operations Oversight | SOP Optimization: Performance Analysis |  | 1 | To find out how well our current rules are working, by reviewing last year’s data and team feedback, in order to identify which parts of the workflow are slow or confusing. | 1. 1 of SOP Evaluation Report (Document) | 3 month(s) and 17 day(s) left |  |  | Ongoing | [7 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: - |  | 2026-02-01 | 2026-12-31
6. Enterprise Operations Oversight | SOP Optimization: Framework Design |  | 2 | To update our goal-setting and work rules, by writing a new draft of the SOP based on the evaluation findings, in order to make our processes faster and easier to follow. | 1. 1 of Updated SOP Draft (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
6. Enterprise Operations Oversight | SOP Optimization: Socialization |  | 3 | To align the team with the new changes, by holding a socialization to discuss the revisions and gather final input, in order to ensure everyone understands how to use the improved system. | 1. 1 of SOP Revision Workshop (Event) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
6. Enterprise Operations Oversight | SOP Optimization: Full Implementation |  | 4 | To activate the improved work standards, by applying the new SOP across all departments for the 2026 cycle, in order to reach higher efficiency and meet our strategic targets. | 1. 1 of New SOP Launch (Event) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
Legal Partner - MOU & Service Agreement with Client
5. Governance, Risk, and Compliance Oversight | Service Agreement: Legal Audit |  | 1 | To identify legal gaps in our global contracts, by reviewing our current clauses with a legal partner against Indonesian, US, and EU laws, in order to receive expert advice on necessary compliance updates. | 1. 1 of Legal Compliance & Gap Report (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue | [7 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
5. Governance, Risk, and Compliance Oversight | Service Agreement: Template Drafting |  | 2 | To create a new standard for client contracts, by writing a revised Master Agreement and MOU based on the legal partner's advice, in order to build a solid draft for final validation. | 1. 1 set of Revised Agreement Draft (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
5. Governance, Risk, and Compliance Oversight | Service Agreement: Template Review |  | 3 | To confirm the safety of our new draft, by presenting the revised templates back to the legal partner for a final check, in order to ensure every clause is legally correct and ready for use. | 1. 1 of Final Legal Approval (Document/Email) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
5. Governance, Risk, and Compliance Oversight | Service Agreement: Internal Socialization |  | 4 | To teach the team how to use the new contracts, by holding a briefing for the sales and admin staff on the updated clauses, in order to ensure all new clients sign the correct version. | 1. 1 of Contract Implementation Session (Event) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
Legal Partner - NDA with Employees
5. Governance, Risk, and Compliance Oversight | Employee NDA: Final Legal Validation |  | 1 | To confirm our employee confidentiality rules, by meeting with our legal partner for a final check of the NDA clauses, in order to ensure the document is fully enforceable under local labor laws. | 1. 1 of Final Legal Validation Meeting (Event) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue | [7 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
5. Governance, Risk, and Compliance Oversight | Employee NDA: Template Finalization |  | 2 | To create the official company secrecy document, by finalizing the Master Employee NDA based on legal feedback, in order to establish a standard form for all current and future staff. | 1. 1 of Approved Master Employee NDA Template (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
5. Governance, Risk, and Compliance Oversight | Employee NDA: Staff Socialization |  | 3 | To teach the team about data safety, by holding an awareness session on confidentiality and intellectual property (IP) rules, in order to make sure everyone knows how to protect company secrets. | 1. 1 of Confidentiality & IP Awareness Session (Event) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
5. Governance, Risk, and Compliance Oversight | Employee NDA: Full Implementation |  | 4 | To secure the company’s legal protection, by collecting signed agreements from all employees, in order to officially activate the new confidentiality protocols across the team. | 1. 1 set of Signed Employee Acknowledgement Record (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
Legal Partner - Data Protection
5. Governance, Risk, and Compliance Oversight | Data Protection: Compliance Audit |  | 1 | To audit our lead generation and marketing steps, by reviewing how we scrape, store, and use data with our legal partner, in order to find any risks under Indonesian, EU, and US privacy laws. | 1. 1 of Data Privacy Gap Analysis Report (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue | [7 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
5. Governance, Risk, and Compliance Oversight | Data Protection: Policy & System Design |  | 2 | To create clear data safety rules, by writing a Master Data Privacy Policy and fixing our data storage flow, in order to make sure our marketing methods follow global regulations. | 1. 1 of Master Data Protection Policy (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
5. Governance, Risk, and Compliance Oversight | Data Protection: Final Legal Validation |  | 3 | To verify our new privacy rules, by showing our updated policies and scraping workflows to the attorney for a final check, in order to ensure LeadGeeks is fully protected from data lawsuits. | 1. 1 of Final Compliance Approval (Document/Email) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
5. Governance, Risk, and Compliance Oversight | Data Protection: Team Socialization |  | 4 | To teach the team about data privacy, by holding a training session on how to handle lead data and outbound emails safely, in order to start the new compliant working way. | 1. 1 of Team Privacy Training Session (Event) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
HKI a. LeadGeeks Inc. (logomark) (optional) b. LeadGeeks Inc. (word mark) c. Alunara (logo mark, word mark) --> nnt di goalsnya dibuat lebih umum seperti stronger ownership of brand, krn belum tahu untuk existing mark, harus ditambah apa
5. Governance, Risk, and Compliance Oversight | HKI: Brand Audit & Legal Strategy |  | 1 | To identify gaps in our brand protection, by reviewing current trademark status for LeadGeeks Inc. and Alunara with our legal partner, in order to decide which new wordmarks and logomarks must be filed. | 1. 1 of IP Gap Analysis Report (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue | [7 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
5. Governance, Risk, and Compliance Oversight | HKI: Asset Preparation & Filing |  | 2 | To apply for official brand ownership, by submitting the required logos and wordmarks to the HKI office (Indonesia) and USPTO (US), in order to secure exclusive rights to our brand names. |  | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
Attend relevant tradeshow
8. Stakeholder and Ecosystem Engagement | Tradeshow: Event Survey |  | 1 | To find the best industry events for LeadGeeks, by researching 2026 tradeshows that match our target audience and services, in order to ensure we invest in the right networking opportunities. | 1. 1 of Tradeshow Research Report (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue | [7 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
8. Stakeholder and Ecosystem Engagement | Tradeshow: Action Planning |  | 2 | To define our success benchmarks, by setting networking KPIs and pre-calculating the required ROI (target deals vs. estimated costs), in order to establish a clear "Win" criteria for the event. | 1. 1 of Event Action Plan & ROI Target Sheet (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
8. Stakeholder and Ecosystem Engagement | Tradeshow: Registration & Logistics |  | 3 | To secure our spot and travel needs, by completing event registration and booking flights and accommodation, in order to ensure all logistics are settled well in advance. | 1. 1 of Registration & Booking Confirmation (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
8. Stakeholder and Ecosystem Engagement | Tradeshow: Preparation |  | 4 | To ready our marketing and sales assets, by finalizing company brochures, pitch decks, and digital lead-capture forms, in order to ensure the team is fully equipped to represent the brand. | 1. 1 of Event Collateral Kit (Document/Assets) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
8. Stakeholder and Ecosystem Engagement | Tradeshow: Event Attendance |  | 5 | To execute our networking strategy, by attending the tradeshow and engaging in pre-scheduled and spontaneous meetings, in order to capture a high volume of new business leads. | 1. 1 of Event Attendance & Lead Log (Event) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
8. Stakeholder and Ecosystem Engagement | Tradeshow: Results Evaluation |  | 6 | To measure the success of the trip, by analyzing lead quality and comparing event costs against potential deal value, in order to determine the total value of the attendance. | 1. 1 of Tradeshow ROI Report (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
|  |  |  | Business Development (incl indonesian projects): - Define business development key focus - Service agreement components (incl pricing) | [12 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
Define new industries or regions.
2. Advancement and Change Governance | Business Development: Status Quo & Ansoff Analysis |  | 1 | To map our current business landscape, by auditing existing services and client locations (Indonesia/Global) using the Ansoff Matrix, in order to establish a clear baseline of our current market reach. | 1. 1 of Ansoff Status Quo Report (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
2. Advancement and Change Governance | Business Development: Strategic Focus & Service Definition |  | 2 | To set the company's expansion path, by defining short, mid, and long-term targets and standardized service agreement components, in order to give the team a clear "Service-Market" focus to execute. | 1. 1 of Master BusDev Strategy Framework (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
2. Advancement and Change Governance | Business Development: Team Socialization & Delegation |  | 3 | To delegate the strategic direction, by presenting the Ansoff growth targets and new service definitions to the BusDev team, in order to align their daily outreach with your high-level vision. | 1. 1 of Strategy Socialization Session (Event) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
2. Advancement and Change Governance | Business Development: Feedback Review & Finalization |  | 4 | To validate the market strategy, by collecting and reviewing feedback from the team regarding market responses and service gaps, in order to finalize the official direction for the 2026 cycle. | 1. 1 of Finalized BusDev Direction (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
Approve Business Development (includes diversification) direction such as talent, tools, and processes
2. Advancement and Change Governance | Business Development: Resource & Process Authorization |  | 1 | To authorize the Business Development "Engine", by assessing and approving the team's proposals for new talent recruitment, sales tools, and operational processes, in order to ensure all resources are budget-aligned and capable of hitting our niche strategic targets. | 1. 1 of Approved BusDev Resource & Process Plan (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
|  |  |  | Commission structure (mau kasih berapa ke sales) untuk program "Commission-Based Sales Program" & "Referral Program" | [12 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
3. Financial Stewardship and Capital Strategy | Commission & Referral: Financial Framework Design |  | 1 | To determine the payout numbers for the Sales and Referral programs, by benchmarking industry standards and calculating company budget margins, in order to provide the BusDev team with the maximum commission limits and fixed referral fees. | 1 of Management Commission & Referral Budget Brief (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
3. Financial Stewardship and Capital Strategy | Commission & Referral: Structure Review & Approval |  | 2 | To approve the final incentive systems, by reviewing the BusDev team’s proposed structures against the pre-set budget guardrails, in order to officially activate the "Commission-Based Sales" and "Referral" programs. | 1. 1 of Approved Commission & Referral Policy (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
7. Market Leadership and Customer Focus |  |  |  | Create workflow to Monitor Industry Trends (in collab with growth): - responsibilities MNG & GRW - outcomes MNG & GRW Karena goals akhir adalah to identify emerging demands and refine our positioning as a niche expert agency. |  | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue | [7 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
7. Market Leadership and Customer Focus | Trend Monitoring: Demand Identification |  | 1 | To capture "emerging demands" in our niche, by scanning high-level sources (e.g. FT Live, industry news) and logging specific client pain points, in order to build a list of potential new service angles. | 1. 1 of Emerging Demand Log (Document/Sheet) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
7. Market Leadership and Customer Focus | Trend Monitoring: Strategic Selection |  | 2 | To define our "Niche Expert" angle, by reviewing the Demand Log and selecting the most profitable emerging trend to focus on, in order to set the strategic direction for the sales team. |  | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
7. Market Leadership and Customer Focus | Trend Monitoring: Delegation |  | 3 | To turn market intelligence into sales action, by briefing the Business Development team on the new demand and how to pitch our expertise, in order to start capturing the newly identified market segment. |  | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
|  |  |  | Approve organizational structures Allocate resources across departments Oversee enterprise risk associated with operations | [12 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
2. Advancement and Change Governance | Growth Dept: Structure & Role Approval |  | 1 | To optimize the Growth team design, by approving the reporting lines AND the specific "Job Descriptions" (JDs) for each niche role, in order to ensure every position has a clear, measurable output that contributes to company revenue. | 1. 1 of Approved Growth Org Chart & Role Definitions (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
2. Advancement and Change Governance | Growth Dept: Cross-Departmental Resource Allocation |  | 2 | To ensure Growth activities support the whole company, by assessing and approving the Growth Dept’s plan for resource delegation to verify they align with the visions of other departments, in order to guarantee that new business wins are manageable. | 1. 1 of Growth-to-Enterprise Alignment Map (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
2. Advancement and Change Governance | Growth Dept: Operational Risk & Performance Oversight |  | 3 | To assist the Growth Dept in identifying enterprise-level risks, by reviewing their operational risk assessments and providing executive guidance on mitigation, in order to ensure the department’s expansion doesn't create unforeseen operations or financial liabilities. | 1. 1 of Growth Risk Oversight Summary (Document) | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue
|  |  |  | Boost Brand Presence Approve Positioning & Messaging. | [12 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
|  |  |  | Represent the organization to key external stakeholders | - Mengikuti persiapan & pelatihan - Melakukan dokumentasi tertulis hasil kegiatan | [11 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
| Promote Amanda’s LinkedIn Presence |  |  | - Penetuan tujuan (bulan 1-2) - Planning - Implementation - Evaluation | [12 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
| Succession Planning |  |  | Establish leadership development strategies Approve succession planning for management positions Monitor enterprise risk Approve organizational structures Allocate resources across departments and functions Oversee enterprise risk associated with operations | 3 positions | [11 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
|  |  |  | Leadership Camp (suggestion after H1/2026 SG evaluation, sekitar awal agustus paling cepatnya) | [12 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
|  |  |  | Review SOP: - Finance (3 SOPs) - Growth | [12 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
|  |  |  | Right person, right role Continue assessing and putting the right people in the right roles (from internal) as there will be significant changes in the company structure. | 1 document of company standardization of the right person, right role | [11 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
|  |  |  | Circle of Safety Trust Feedback is rewarded Conflict Management | Bikin guide book u/ leaders Per quater 1 topic dari quarter 2 | [11 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
FBA Bonus System
3. Financial Stewardship and Capital Strategy | FBA Bonus System: Factors Identification |  | 1 | To identify key performance indicators, by analyzing operational milestones, in order to establish a fair baseline for first-year rewards. | 1. 1 document of Approved Bonus Factor List | Overdue by 1520 month(s) and 15 day(s) | Not started |  | Overdue | Breakthrough | MNG | MNG | HRD, FAC, FBA | Yes | Program | Occasional | 1. Complexity Mid 2. Frequency Low 3. Execution Period Low | We are strong at defining clear KPIs and operational milestones, and we already have experience structuring performance frameworks. This allows us to translate daily FBA operations into measurable, fair bonus factors. | As a first-year operation, we do not yet have long-term performance data, which makes baseline setting more challenging. Without this structured effort, decisions would rely too much on assumptions. | We have access to operational data, internal documentation, and team input that can be consolidated into a transparent bonus framework. This positions us to build trust and set a scalable incentive model early. | If we do not formalize bonus factors now, rewards may appear subjective or inconsistent, which can damage motivation and credibility. This risk increases as the team and workload grow. | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Talent & Culture | 2026-02-01 | [65 empty] | Amanda
3. Financial Stewardship and Capital Strategy | FBA Bonus System: Workflow Design |  | 2 | To design a structured bonus workflow, by mapping internal approval steps, in order to ensure transparent and timely payouts. | 1. 1 document of FBA Bonus System Workflow | Overdue by 2 month(s) and 15 day(s) | Not started |  | Overdue | Breakthrough | MNG | MNG | HRD, FAC | Yes | Program | Occasional | 1. Complexity High 2. Frequency High 3. Execution Period Mid | We are strong in designing structured processes and approval flows, and we consistently document workflows to ensure clarity. This makes us well-positioned to create a reliable bonus payout process. | Without a defined workflow, bonus approvals risk delays, miscommunication, and confusion over responsibilities. Manual handling increases the chance of errors. | We already have internal tools, documented processes, and cross-functional collaboration that can be leveraged to standardize bonus approvals. This enables more transparent payouts. | If a clear workflow is not established, delayed or inconsistent payouts may reduce trust and negatively impact team morale and performance. | Budget: -YES Human resource: -NO Time: -NO Technology: -YES | Unavailable resources: - Human resource - Time Plan moving forward: - | Company Establishment - Talent & Culture | 2026-02-01 | 2026-06-30 | [64 empty] | Amanda
3. Financial Stewardship and Capital Strategy | FBA Bonus System: Review |  | 3 | To validate the incentive framework, by auditing budget availability and payout fairness, in order to ensure financial sustainability and team equity. | 1. 1 document of Review Meeting Report | Overdue by 2 month(s) and 15 day(s) | Not started |  | Overdue | Breakthrough | MNG | MNG | HRD, FAC | Yes | Program | Occasional | 1. Complexity Mid 2. Frequency Mid 3. Execution Period Mid |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: - | Company Establishment - Talent & Culture | 2026-02-01 | 2026-06-30 | [64 empty] | Amanda
3. Financial Stewardship and Capital Strategy | FBA Bonus System: Implementation |  | 4 | To launch the FBA bonus system, by formally presenting terms to the team and implementing the bonus system accordingly, in order to drive high performance and employee retention. | 1. 1 event of Bonus System Team Socialization 2. 1 Bonus Tracking Document for Transparent Calculation and Approval | 3 month(s) and 17 day(s) left | Not started |  | Ongoing | Breakthrough | MNG | MNG | HRD, FAC, FBA | Yes | Program | Occasional | 1. Complexity High 2. Frequency High 3. Execution Period High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: - | Company Establishment - Talent & Culture | 2026-07-01 | 2026-12-31 | [64 empty] | Amanda, Margaretha
|  |  |  | Evaluasi SG system that enables PMS implementation | - PMS workflow | [11 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
|  |  |  | Business Development Coaching from NEDP | [12 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
|  |  |  | Top management to create a standardized cross-functional SOP about collaboration & communication --> Clarify and Document Cross-Functional Expectation Norms. Work with the leadership team to clarify a universal standard for cross-functional deliverables, focusing on mandatory communication protocols when a deadline or quality standard cannot be met. | [12 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
|  |  |  | SG menentukan tentang penilaian tercapainya sebuah goals --> karena hubungannya sama PMS dan bukan lagi tetntang tercapai atau tidak tapi juga kualitas | [12 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
[17 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
[17 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
[17 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
[17 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
[17 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
[17 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
[17 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
[17 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
[17 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
[17 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
[17 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
[17 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
[17 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
[17 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
[17 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
[17 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -
[17 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Low/Mid/High |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: -

## FAC (hidden)
Department Functions | Department Goals | Department Goals (Specific) | Indicators (Measurable) | Day Counter | Status | Date of Accomplishment | Accomplishment Status | Goals Type | Owner | PIC | Collaborators | Collaboration | Type | Period | Expectations for Collaborators | Strengths | Weaknesses | Opportunities | Threats | Resources Availability (Attainable) | Resources Invailability (Attainable) | Company Goals Reference (Relevance) | Start date (Time bound) | End date (Time bound) | Notes | Half Adjustment | Updated Goal_Initial | Updated Goal_Reason | Updated Specific_Initial | Updated Specific_Reason | Updated Measurable_Initial | Updated Measurable_Reason | Updated Attainable_Initial | Updated Attainable_Reason | Updated Relevant_Initial | Updated Relevant_Reason | Updated Time-Bound_Initial_Start | Updated Time-Bound_Initial_End | Updated Time-Bound_Reason | Additional Note | Indicators Achievement January | Result (Link) January | Challenge January | Homework January | Indicators Achievement February | Result (Link) February | Challenge February | Homework February | Indicators Achievement March | Result (Link) March | Challenge March | Homework March | Indicators Achievement April | Result (Link) April | Challenge April | Homework April | Indicators Achievement May | Result (Link) May | Challenge May | Homework May | Indicators Achievement June | Result (Link) June | Challenge June | Homework June | Indicators Achievement July | Result (Link) July | Challenge July | Homework July | Indicators Achievement August | Result (Link) August | Challenge August | Homework August | Indicators Achievement September | Result (Link) September | Challenge September | Homework September | Indicators Achievement October | Result (Link) October | Challenge October | Homework October | Indicators Achievement November | Result (Link) November | Challenge November | Homework November | Indicators Achievement December | Result (Link) December | Challenge December | Homework December
ROW FOR ARRAYFORMULA ¦¦ DO NOT CHANGE
5. Systems & Policy Management | [Department Goals] | SOP Tax (PPh21 Karyawan, PPh21 Non Karyawan, PPh23, PPh26) contoh tentang tax treaty dgn USA dan pakai jasa dari LN | [Measurable] | Overdue by 8 month(s) and 14 day(s) |  | 2025-12-02 | Completed: Early | [7 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long |  |  |  |  | Budget: -YES/NO Human resource: -YES/NO Time: -YES/NO Technology: -YES/NO | Unavailable resources: - Plan moving forward: - |  | 2025-12-01 | 2025-12-31
1. Financial Management (Finance) |  | Commission structure (mau kasih berapa ke sales) untuk program "Commission-Based Sales Program" & "Referral Program" |  | Overdue by 1520 month(s) and 15 day(s) |  |  | Overdue |  |  |  | MNG | Yes |  | Occasional | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long
|  | Emergency Fund (incl managing the saving plan) | [12 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long
|  | Financial Analysis & Planning (karena salah satu yg mau dilihat dari insight-nya adalah untuk compensation planning 2026) | [12 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long
|  | Big goal / priority: Review existing system, create and execute improvement system | [12 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long
|  | Perform financial analysis Create financial plan and analysis for both businesses to understand its investment and gain. | [12 empty] | 1. Complexity Low/Mid/High 2. Frequency Low/Mid/High 3. Execution Period Short/Mid/Long
Formulas:
Accomplishment Status = IF(ISBLANK([Department Functions]:A50), "", IF(NOT(ISBLANK([Date of Accomplishment]:G50)), IF([Date of Accomplishment]:G50 < [End date (Time bound)]:Y50, "Completed: Early", IF([Date of Accomplishment]:G50 = [End date (Time bound)]:Y50, "Completed: On Time", "Completed: Late") ), IF(TODAY() < [Start date (Time bound)]:X50, "Not Started", IF(TODAY() <= [End date (Time bound)]:Y50, "Ongoing", "Overdue") ) ) )

## ITE
Department Functions | Department Goals | Department Goals (Specific) | Indicators (Measurable) | Day Counter | Status | Date of Accomplishment | Accomplishment Status | Goals Type | Owner | PIC | Collaborators | Collaboration | Type | Period | Expectations for Collaborators | Strengths | Weaknesses | Opportunities | Threats | Resources Availability (Attainable) | Resources Invailability (Attainable) | Company Goals Reference (Relevance) | Start date (Time bound) | End date (Time bound) | Notes | Half Adjustment | Updated Goal_Initial | Updated Goal_Reason | Updated Specific_Initial | Updated Specific_Reason | Updated Measurable_Initial | Updated Measurable_Reason | Updated Attainable_Initial | Updated Attainable_Reason | Updated Relevant_Initial | Updated Relevant_Reason | Updated Time-Bound_Initial_Start | Updated Time-Bound_Initial_End | Updated Time-Bound_Reason | Additional Note | Indicators Achievement January | Result (Link) January | Challenge January | Homework January | Indicators Achievement February | Result (Link) February | Challenge February | Homework February | Indicators Achievement March | Result (Link) March | Challenge March | Homework March | Indicators Achievement April | Result (Link) April | Challenge April | Homework April | Indicators Achievement May | Result (Link) May | Challenge May | Homework May | Indicators Achievement June | Result (Link) June | Challenge June | Homework June | Indicators Achievement July | Result (Link) July | Challenge July | Homework July | Indicators Achievement August | Result (Link) August | Challenge August | Homework August | Indicators Achievement September | Result (Link) September | Challenge September | Homework September | Indicators Achievement October | Result (Link) October | Challenge October | Homework October | Indicators Achievement November | Result (Link) November | Challenge November | Homework November | Indicators Achievement December | Result (Link) December | Challenge December | Homework December
| ROW FOR ARRAYFORMULA ¦¦ DO NOT CHANGE | [5 empty] | #REF!
Website Management | New Website Enhancement and Technical SEO Optimization | To enhance the new company website by regularly updating content, refining the design and layout structure, improving user experience, and implementing technical SEO optimization, in order to increase online visibility, improve overall SEO performance, and strengthen the company’s brand presence. | Action: Update the new website’s content, design and layout, improve user experience, and optimize SEO performance, while ensuring optimal functionality and maintaining integration with analytics tools. Target: - Implement 100% of approved updates for technical website refinements and SEO optimization. - Resolve 100% of identified technical issues, including functionality errors and other technical issues. The Way: - Conduct regular updates and improvements to website content, design, and layout. - Conduct regular testing to ensure optimal platform functionality and fix technical issues. - Provide ongoing technical support for SEO optimization and maintain seamless integration with analytics tools (GA, GSC, GTM). | 3 month(s) and 17 day(s) left | In Progress |  | Ongoing | Improvement | ITE | ITE | ITE, MNG, OPS, GRW, EXP, HRD | Yes | Program | Periodic | 1. Complexity Low 2. Frequency High 3. Execution Period Long | - Improves website content, structure, layout, design, functionality, and overall usability aligned with business growth. - Enhances brand visibility, credibility, professionalism, and overall digital presence. - Website improvements can be implemented incrementally and progressively. | - Ongoing updates require consistent time, effort, prioritization, and coordination. - SEO impact takes time before measurable results are visible. | - Strong SEO performance drives sustainable organic traffic growth while enhancing search rankings, brand authority, and credibility. - Website optimization supports new services development, while a strong digital presence enables long-term business growth. | - Competitors might have better web presence and invest more aggressively in UX and SEO. - Search engine algorithm changes may negatively impact SEO performance and rankings. | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Profitability - Customer Acquisition | 2026-01-01 | 2026-12-31 |  | No Adjustment | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | In Progress | - List of Website Management Tasks and Plans | - | - | In Progress | - List of Website Management Tasks and Plans | - | - | In Progress | - List of Website Management Tasks and Plans | - | - | In Progress | - List of Website Management Tasks and Plans | - | - | In Progress | - List of Website Management Tasks and Plans | - | - | In Progress | - [None for this month] | - | - | In Progress | - List of Website Management Tasks and Plans | - | - | In Progress | - [None for this month] | - | -
Infrastructure Management | Google Workspace Capability Exploration | To gain deeper insight into the main productivity platform’s capabilities by learning and exploring Google Workspace features and configurations, in order to identify practical opportunities to improve platform operations, productivity, and overall effectiveness. | Action: Explore Google Workspace features, configurations, and administrative capabilities. Target: - Create 1 comprehensive Google Workspace capability exploration document covering core services, admin features, and security controls. The Way: - Review official Google Workspace documentation and Admin Console settings. - Explore Google Workspace features directly through the Admin Console. - Document exploration results and identify potential improvement opportunities. | Congratulations! This goal has been completed! | Completed | 2026-03-10 | Completed: Early | Improvement | ITE | ITE | ITE | No | Program | Occasional | 1. Complexity Mid 2. Frequency Low 3. Execution Period Short | - Leverages widely adopted, reliable, and industry-standard Google ecosystem tools. - Centralized admin console simplifies configuration review and documentation. - Strong integration across email, drive, collaboration, and automation tools. | - Limited internal expertise in advanced Google Workspace architecture. - Documentation quality depends heavily on consistency and technical depth. | - Identifies optimization opportunities for security, automation, collaboration, and governance. - Builds foundation for standardized workflows and scalable IT governance. | - Misinterpretation of features or configurations may lead to poor recommendations. - Rapid platform updates may cause documentation to become outdated quickly. | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Technology Innovation | 2026-02-01 | 2026-03-31 |  | No Adjustment | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not started | N/A | - | - | In Progress | - Google Workspace Documentation | - | - | Completed | - Google Workspace Documentation - Completed at March, 10, 2026. | - | - Continue creating the assessment framework for Google Workspace. | Completed | - Completed at March, 10, 2026. | - | - | Completed | - Completed at March, 10, 2026. | - | - | Completed | - Completed at March, 10, 2026. | - | - | Completed | - Completed at March, 10, 2026. | - | - | Completed | - Completed at March, 10, 2026. | - | -
Infrastructure Management | Google Workspace Platform Assessment | To assess the effectiveness of the existing main productivity platform by reviewing and evaluating Google Workspace features and settings based on exploration results, in order to identify gaps, inefficiencies, and optimization opportunities that will improve platform utilization and operational performance. | Action: Review and assess current Google Workspace configurations and usage based on exploration results. Target: - Complete 1 comprehensive Google Workspace platform assessment document covering administrative settings, security controls, and usage effectiveness. The Way: - Review existing configurations against Google Workspace best practices. - Analyze Admin Console settings and security controls. - Compare current usage with capabilities identified during the exploration phase. - Document assessment results and provide improvement recommendations. | Congratulations! This goal has been completed! | Completed | 2026-07-10 | Completed: Late | Improvement | ITE | ITE | ITE | No | Program | Periodic | 1. Complexity Mid 2. Frequency Low 3. Execution Period Short | - Leverages documented findings and learning results from the exploration phase. - Provides objective visibility into current system effectiveness and gaps. - Low cost assessment using existing tools and internal resources | - Assessment quality depends on completeness and accuracy of exploration data. - May reveal gaps that cannot be immediately addressed due to budget or resources. | - Identifies inefficiencies, unused features, security gaps, and governance weaknesses. - Strengthens alignment between IT operations and business productivity needs. | - Incomplete assessment may overlook critical risks or inefficiencies. - Platform changes during assessment may affect consistency. | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Technology Innovation | 2026-04-01 | 2026-06-30 |  | No Adjustment | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | In Progress | - DRAFT - Google Workspace Assessment | - | - Continue creating the assessment framework for Google Workspace. | In Progress | - [None for this month] | - | - Continue creating the assessment framework for Google Workspace. | In Progress | - DRAFT - Google Workspace Assessment - Google Workspace Capability Assessment | - Need to create and finalize the assessment framework. However, mapping Google Workspace capabilities is complex due to its broad scope. | - Continue creating and finalizing the assessment framework for google Workspace. - Assess the current Google Workspace capabilities. | Completed | - Google Workspace Capability Assessment - Completed at July, 10, 2026. | - | - Continue doing the action items and tasks based on the assessment framework. | Completed | - Completed at July, 10, 2026. | - | -
Infrastructure Management | Google Workspace Platform Enhancement | To improve the effectiveness of the main productivity platform by optimizing and enhancing Google Workspace features and settings based on assessment results, in order to increase user productivity, improve operational efficiency, and ensure reliable and stable system performance. | Action: Optimize and enhance Google Workspace features and configurations based on assessment results. Target: - Implement 100% of the improvement actions identified as top priority in the assessment results. The Way: - Prioritize improvement items based on impact and feasibility. - Configure and apply Google Workspace changes through the Admin Console. - Inform to stakeholders and review configuration changes to ensure system stability. | 0 month(s) and 16 day(s) left | Not started |  | Not Started | Breakthrough | ITE | ITE | ITE, MNG, OPS, GRW, EXP, HRD, FAC, FBA | Yes | Program | Periodic | 1. Complexity Mid 2. Frequency Low 3. Execution Period Short | - Directly improves productivity, reliability, and security. - Uses existing platform investments without large infrastructure changes. - Platform supports flexible configuration changes without major downtime. | - Potential temporary disruption during configuration changes. - Some enhancements may depend on limited and paid licensing or feature. | - Increases operational efficiency and collaboration quality. - Supports future integration with cloud services and analytics. | - Misconfiguration may impact security, availability, or user access. - Platform updates from Google may change behavior or controls. | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Technology Innovation | 2026-07-01 | 2026-09-30 |  | No Adjustment | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | -
Infrastructure Management | Google Cloud Capability Exploration | To identify scalable cloud capabilities for IT infrastructure modernization by learning and exploring Google Cloud services for data integration, backups, and analytics, in order to support scalable infrastructure, efficient data management, and data-driven decision-making. | Action: Learn and explore Google Cloud services relevant to data integration, backups, and analytics. Target: - Create 1 documented overview of relevant Google Cloud services, including potential use cases and implementation recommendations. The Way: - Research Google Cloud services and architectures relevant to company needs. - Document exploration results and provide recommendations for future implementation. | 3 month(s) and 17 day(s) left | In Progress |  | Not Started | Breakthrough | ITE | ITE | ITE | No | Program | Occasional | 1. Complexity Mid 2. Frequency Low 3. Execution Period Mid | - Leverages scalable and enterprise-grade cloud infrastructure ecosystem. - Supports modern architectures for data, backups, and analytics. - Strong integration with the existing Google Workspace ecosystem. | - Limited cloud architecture expertise internally. - Complexity of cloud architecture increases learning effort. | - Enables future modernization of infrastructure and data architecture. - Opens opportunities for AI, BI, and advanced integrations. | -Rapid technology evolution may outpace learning outcomes. - Unexpected cloud costs due to misconfiguration or uncontrolled usage. | Budget: -NO Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Technology Innovation | 2026-04-01 | 2026-12-31 |  | No Adjustment | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | In Progress | - Google Cloud Documentation | - | - | In Progress | - [None for this month] | - | -
Infrastructure Management | Company Email Domain Migration | To update the company’s email domain by migrating all company email accounts from leadgeeksprospecting.com to leadgeeksinc.com with minimal technical disruption, in order to strengthen brand identity, improve email credibility, and ensure reliable internal and external communication. | Action: Migrate all company email accounts from the old domain to the new company domain (leadgeeksinc.com). Target: - Migrate 100% of active company email accounts to the new domain (leadgeeksinc.com). The Way: - Identify and select appropriate technical methods for email migration. - Coordinate the migration schedule with stakeholders to minimize technical disruptions. - Develop and execute an email migration plan. | Congratulations! This goal has been completed! | Completed | 2026-06-29 | Completed: Early | Breakthrough | ITE | ITE | ITE, MNG, OPS, GRW, EXP, HRD, FAC, FBA | Yes | Program | Occasional | 1. Complexity Low 2. Frequency Low 3. Execution Period Short | - Improves brand consistency, professionalism, and company identity. - Centralizes and standardizes email communication under a single company domain. - Enhances email security, reliability, and policy enforcement. | - Requires careful planning, coordination, and execution. - Temporary operations disruption and communication issues during transition or if migration is poorly executed. | - Strengthens corporate branding and credibility externally. - Increase trust and recognition with potential clients, partners, and stakeholders. | - Risk of email delivery, access, routing, or configuration issues during migration process. - Potential operational disruption or data loss if technical issues are not resolved quickly. | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Technology Innovation | 2026-03-01 | 2026-04-30 |  | No Adjustment | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not started | N/A | - | - | Not started | N/A | - | - | In Progress | - Email Domain Migration Guidelines and Playbook - Email Domain Migration Plan and Backlog | - | - Further exploration of Email Domain Migration is still needed to create the plan and guidelines. | In Progress | - Email Domain Migration Guidelines and Playbook - Email Domain Migration Plan and Backlog - The new company email domain has been active since April 2026 and is currently serving as a secondary domain, running in parallel with the old domain during the transition period before the old domain is deactivated. | - | - Continue doing the action items and tasks after migration based on the backlog and timeline. | In Progress | - Email Domain Migration Guidelines and Playbook - Email Domain Migration Plan and Backlog - The new company email domain has been active since April 2026 and is currently serving as a secondary domain, running in parallel with the old domain during the transition period before the old domain is deactivated. - Employees have started using the new domain and completed the action items, such as updating the default sender email in Gmail, testing email functionality (send and receive), updating email signatures, and updating login credentials in tools and applications. | - | - Continue doing the action items and tasks after migration based on the backlog and timeline. | Completed | - Email Domain Migration Guidelines and Playbook - Email Domain Migration Plan and Backlog - The new company email domain has been active since April 2026. As initially planned, both the old and new domains remained active simultaneously during the transition period until July 1, 2026. However, the old domain will remain active as a secondary domain because its subscription has been renewed for this year. - Change the primary domain in the Google Admin Console to the new company domain. - Migrate the DNS configuration for the old domain from Vultr to Hostinger. - Completed at June, 29, 2026. | - | - | Completed | - Completed at June, 29, 2026. | - | - | Completed | - Completed at June, 29, 2026. | - | -
Infrastructure Management | Company Email Domain Post-Migration Monitoring | To stabilize the company’s new email domain system after migration by monitoring system performance and ensuring a smooth transition without disrupting internal and external communication, in order to ensure uninterrupted business communications, minimize post-migration operational risks, and maintain operational stability. | Action: Monitor email system performance after domain migration. Target: - Resolve 100% of identified post-migration technical issues within the monitoring period. The Way: - Collect technical issue reports from users and stakeholders. - Monitor email system functionality and promptly address any post-migration issues. | Congratulations! This goal has been completed! | Completed | 2026-06-30 | Completed: On Time | Improvement | ITE | ITE | ITE, MNG, OPS, GRW, EXP, HRD, FAC, FBA | Yes | Program | Occasional | 1. Complexity Low 2. Frequency Low 3. Execution Period Short | - Ensures system stability and operational continuity after migration. - Allows early detection of configuration or delivery issues. - Protects business continuity and communication reliability. | - Monitoring activities are mostly manual without dedicated tools. - Requires continuous monitoring effort and technical attention. | - Optimize performance and user experience. - Improves long-term email performance and security posture. | - Insufficient monitoring may allow unnoticed disruptions. - Delayed response to problems may impact business continuity. | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Technology Innovation | 2026-05-01 | 2026-06-30 |  | No Adjustment | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | In Progress | - Email Log Monitoring - April | - | - Continue doing the monitors email performance, including email delivery, delays, and potential spam issues, while also handling any technical issues. | In Progress | - Email Log Monitoring - May - Email Log Search Results | - | - Continue doing the monitors email performance, including email delivery, delays, and potential spam issues, while also handling any technical issues. | Completed | - Email Log Monitoring - June - Email Log Search Results - Completed without any technical issues during the period from April 24 to June 30, 2026. - Completed at June, 30, 2026. | - | - | Completed | - Completed at June, 30, 2026. | - | - | Completed | - Completed at June, 30, 2026. | - | -
Cybersecurity | Company Security Assessment | To assess the company’s security measures by conducting security reviews aligned with GDPR and other security standards, in order to identify security risks, ensure regulatory compliance, and protect company systems and data. | Action: Conduct a comprehensive company security assessment aligned with GDPR and current security standards. Target: - Complete 1 comprehensive security assessment aligned with GDPR and other security standards. The Way: - Conduct security assessments based on GDPR and other security standards to identify gaps and areas for improvement. - Document security assessment results and provide recommendations for risk mitigation actions. | 3 month(s) and 17 day(s) left | Not started |  | Not Started | Improvement | ITE | ITE | ITE, MNG | Yes | Program | Periodic | 1. Complexity Mid 2. Frequency Low 3. Execution Period Mid | - Improves overall security posture by identifying vulnerabilities, gaps, and threat exposure. - Aligns security practices with GDPR and industry standards. - Enhances organizational security awareness and reduces overall cyber risk exposure. | - Requires specialized and advanced security knowledge. - Manual assessments may miss hidden vulnerabilities. | - Stronger alignment with industry best practices and compliance requirements. - Supports compliance readiness and audit preparedness. | - Rapidly evolving cyber threats may outpace implemented controls. - Incomplete assessments may leave potential vulnerabilities unaddressed. | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Technology Innovation | 2026-07-01 | 2026-12-31 |  | No Adjustment | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not started | -N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | -
Cybersecurity | Security Control Optimization | To strengthen the company’s security measures by optimizing existing security controls based on assessment results, in order to reduce security vulnerabilities and enhance overall security defenses. | Action: Optimize existing security controls based on security assessment results. Target: - Implement at least 70% of identified and prioritized security improvements based on assessment results. The Way: - Enhance and optimize existing security controls and measures based on assessment results. - Prioritize security improvements based on risk level and impact. - Inform to stakeholders and review configuration changes to ensure system stability. | 3 month(s) and 17 day(s) left | Not started |  | Not Started | Improvement | ITE | ITE | ITE, MNG, OPS, GRW, EXP, HRD, FAC, FBA | Yes | Program | Periodic | 1. Complexity Mid 2. Frequency Low 3. Execution Period Mid | - Directly reduces security gaps identified in assessments. - Improves overall resilience of systems and data. - Strengthens enforcement of security policies. | - Optimization effort may increase operational complexity. - Requires continuous maintenance and policy enforcement. | - Gradual improvement toward a mature security framework. - Reduces long-term risk of incidents and breaches. | - New threats may emerge beyond optimized controls. - Configuration errors may introduce new risks. | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Technology Innovation | 2026-07-01 | 2026-12-31 |  | No Adjustment | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | -
Cybersecurity | New Company Email Implementation | To establish controlled and secure company email systems by implementing a new email domain (leadgeeksinc.co) and creating new accounts using the domain, in order to reduce unauthorized access and enforce consistent company-wide email security standards. | Action: Implement new company email accounts using the leadgeeksinc.co domain. Target: - Ensure that 100% of employees use company Google Workspace email accounts. The Way: - Create Google Workspace email accounts for all employees using the leadgeeksinc.co domain. - Enforce email account security standards. - Manage and maintain email accounts through the Admin Console. | Congratulations! This goal has been completed! | Completed | 2026-06-23 | Completed: Early | Breakthrough | ITE | ITE | ITE, OPS, GRW | Yes | Program | Occasional | 1. Complexity Low 2. Frequency Low 3. Execution Period Short | -Establishes controlled identity management and secure communication baseline. - Reduces unauthorized access and data leakage risks. - Supports compliance and access governance. | - Requires ongoing monitoring and access reviews. - Relies on employee compliance and awareness. | -Strengthens data protection and internal controls. - Improves professional communication standards. | - Credential compromise or phishing incidents. - External integrations creating security gaps. | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Technology Innovation | 2026-05-01 | 2026-06-30 |  | No Adjustment | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | In Progress | - New Company Account Implementation Plan and Backlog | - | - Create a new company email domain, @leadgeekinc.co, and set up new company email accounts for employees. | In Progress | - New Company Account Implementation Plan and Backlog - Subscribe new Google Workspace plan for Business Starter flexible plan. - Configure the DNS, email domain server, and Google Admin Console settings for the new Google Workspace environment. - Create and configure the Google Workspace administrator account and security setting. - Review and implement all necessary settings within the Google Admin Console for the new domain. - Create and configure new Google Workspace user accounts under the new domain, including user access and permissions, security settings, and email signature. - Test the functionality of Google Workspace tools and services, email delivery, account access, and administrative features. - Create documentation for new company account policy. | - | - Continue doing the action items and tasks after new company email implementation based on the backlog and timeline. | Completed | - New Company Account Implementation Plan and Backlog - Reassign and update three existing Google Workspace user accounts from former employees to new employees, including user information, account access and permissions, security settings, and email signatures. - Test the functionality of Google Workspace tools and services, email delivery, account access, and administrative features after the reassignment. - Distribute the new company account login information, along with the instructions and policy. - Completed at June, 23, 2026. | - | - | Completed | - Completed at June, 23, 2026. | - | - | Completed | - Completed at June, 23, 2026. | - | -
Cybersecurity | Data Security and Access Control Enhancement | To enhance company-wide data security and access control by reviewing Google Drive file and folder sharing permissions, removing irrelevant access, and maintaining updated Google Group memberships, in order to prevent unauthorized data access, reduce data leakage risks, and ensure compliance with data protection standards. | Action: Review and optimize Google Drive sharing and Google Group access control. Target: - Ensure that 100% of files and folders in Google Drive are not shared with irrelevant or unauthorized users. The Way: - Review current file and folder sharing permissions in Google Drive to identify and remove irrelevant or unauthorized access. - Regularly review and maintain Google Group memberships, updating them as necessary. | 3 month(s) and 17 day(s) left | Not started |  | Not Started | Breakthrough | ITE | ITE | ITE, MNG, OPS, GRW, EXP, HRD, FAC, FBA | Yes | Program | Periodic | 1. Complexity Low 2. Frequency Mid 3. Execution Period Mid | - Protects sensitive company and client data from unauthorized access, strengthening overall data security. - Builds trust with clients and stakeholders through effective data handling practices. - Focuses on protecting company and client data while aligning with best practices for data management. | - Requires continuous monitoring, audits, and periodic access reviews, which can be time-consuming and prone to manual errors. - Effectiveness depends on employee awareness, behavior, and ongoing compliance with policies and controls. | - Improved data security reduces risk of data breaches and unauthorized access. - Improves data integrity and enhances compliance with data protection regulations. | - Human error during permission assignment or access reviews. - Potential risks from third-party apps or tools integrations and external data sharing. | Budget: -NO Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Technology Innovation | 2026-07-01 | 2026-12-31 |  | No Adjustment | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | -
Technology Optimization & Innovation | Existing App Script System Evaluation | To assess daily workflow automation and evaluate the effectiveness of existing automation systems by evaluating Apps Script systems implemented in 2024 and 2025, in order to increase daily work efficiency and overall operational effectiveness. | Action: Evaluate existing App Script automation systems implemented in 2024 and 2025. Target: - Create 1 document summarizing the Apps Script evaluation results based on feedback surveys. The Way: - Conduct feedback evaluations of existing App Script systems in Operations, HRD, Experience, Finance, and the company to identify areas for improvement. | Congratulations! This goal has been completed! | Completed | 2026-02-27 | Completed: Early | Improvement | ITE | ITE | ITE, MNG, OPS, HRD, EXP, FAC | Yes | Program | Annual | 1. Complexity Low 2. Frequency Low 3. Execution Period Short | - App Script can be integrated with all Google Workspace tools. - Existing App Script system streamlined processes and reduced manual work. - Improves operational efficiency and effectiveness across multiple departments. | - Limited resource may slow down development, testing, and execution. - Potential knowledge gaps in App Script systems and advanced automation techniques. | - Optimizing existing App Scripts can resolve current system issues and bugs. - Enhancing existing automated processes may improve employee satisfaction and productivity. | - Unexpected complexities in App Script systems could cause delays. - Errors during optimization could disrupt daily operations. | Budget: -NO Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Technology Innovation | 2026-02-01 | 2026-02-28 |  | No Adjustment | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not started | N/A | - | - | In Progress | - Evaluasi Implementasi dan Penggunaan App Script di LeadGeeks (Responses) - https://www.canva.com/design/DAHCx8K2NVI/5JZy3zAitCWO1oHv1FGsDQ/edit?ui=eyJBIjp7fX0 - Completed at February, 27, 2026. | - | - App Script evaluation results will be presented and the action item will be executed. | Completed | - Completed at February, 27, 2026. | - | - App Script evaluation results will be presented and the action item will be executed. | Completed | - Completed at February, 27, 2026. | - | - | Completed | - Completed at February, 27, 2026. | - | - | Completed | - Completed at February, 27, 2026. | - | - | Completed | - Completed at February, 27, 2026. | - | - | Completed | - Completed at February, 27, 2026. | - | -
Technology Optimization & Innovation | Existing App Script System Optimization | To enhance daily workflow automation and improve the effectiveness of existing automation systems by optimizing existing Apps Script systems, in order to increase daily work efficiency and overall operational effectiveness. | Action: Optimize existing App Script automation systems implemented accross department and company. Target: - Complete 100% optimization of identified App Script systems based on App Script evaluation results and bug or error findings. The Way: - Coordinate with relevant departments to identify bugs or errors found in Apps Script systems. - Implement necessary updates through development, testing, and system deployment based on App Script evaluation results and bug or error findings. | 3 month(s) and 17 day(s) left | In Progress |  | Ongoing | Improvement | ITE | ITE | ITE, MNG, OPS, GRW, EXP, HRD, FAC, FBA | Yes | Program | Occasional | 1. Complexity Low 2. Frequency Low 3. Execution Period Long | - App Script can be integrated with all Google Workspace tools. - Existing App Script system streamlined processes and reduced manual work. - Improves operational efficiency and effectiveness across multiple departments. | - Limited resource may slow down development, testing, and execution. - Potential knowledge gaps in App Script systems and advanced automation techniques. | - Optimizing existing App Scripts can resolve current system issues and bugs. - Enhancing existing automated processes may improve employee satisfaction and productivity. | - Unexpected complexities in App Script systems could cause delays. - Errors during optimization could disrupt daily operations. | Budget: -NO Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Technology Innovation | 2026-02-01 | 2026-12-31 |  | No Adjustment | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not started | N/A | - | - | In Progress | - App Script Tasks and Management - Archived Asset List PT Lead Geeks Indonesia - Major Holiday in US EU ID SG | - | - | In Progress | - DE - Email Response Tracking - App Script Tasks and Management | - | - Execute action items from App Script Evaluation Results to optimize and enhance the existing App Script systems. | In Progress | - [None for this month] | - | - | In Progress | - [None for this month] | - | - | In Progress | - [None for this month] | - | - | In Progress | - [None for this month] | - | - | In Progress | - App Script Tasks and Management - Archived Asset List PT Lead Geeks Indonesia - Fix bugs and errors in the existing Apps Script system for Device Checking. | - | -
Technology Optimization & Innovation | New App Script System Implementation | To create daily workflow automation and improve internal process efficiency by developing and implementing new Apps Script systems, in order to reduce manual work, increase daily work efficiency, and enhance long-term operational effectiveness. | Action: Develop and implement new daily workflow automation systems using App Script. Target: - Implement at least 8 new App Script systems across departments and the company. The Way: - Identify the specific needs and requirements for new App Script systems. - Execute the implementation through development, testing, and system launch based on identified needs and requirements. | 3 month(s) and 17 day(s) left | In Progress |  | Ongoing | Breakthrough | ITE | ITE | ITE, MNG, OPS, GRW, EXP, HRD, FAC, FBA | Yes | Program | Annual | 1. Complexity Mid 2. Frequency Mid 3. Execution Period Long | - App Script can be integrated with all Google Workspace tools. - New App Script systems can address specific needs of the company. - Improves operational efficiency and effectiveness across multiple departments. | - Limited resource may slow down development, testing, and execution. - Potential knowledge gaps in App Script systems and advanced automation techniques. | - Implementing new App Scripts can address department specific needs and goals. - Potential to significantly reduce repetitive manual tasks by implementing new automated processes. | - Unexpected complexities in App Script systems could cause delays. - Errors after implementation could disrupt daily operations. | Budget: -NO Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Technology Innovation | 2026-02-01 | 2026-12-31 |  | No Adjustment | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | In Progress | - IT App Script Task & Progress Tracker - Prototype Customer Invoice Masterlist (In Progress) | - | - | In Progress | - IT App Script Task & Progress Tracker - Prototype Customer Invoice Masterlist (In Progress) | - | - Implement the new App Script code and settings for Invoice System. | In Progress | - IT App Script Task & Progress Tracker - Prototype Customer Invoice Masterlist (In Progress) - Implemented 1 new Apps Script for the Invoice System out of the target of 8 Apps Script systems. | - |  | In Progress | - IT App Script Task & Progress Tracker - Template Migration - Company Expenditure & Authorization Form - Implemented 1 new Apps Script for the Project Data Migration process in Operations, increasing the total to 2 out of the target of 8 Apps Script systems. - Developed 1 new Apps Script for financial transaction workflow automation. | - | - | In Progress | - IT App Script Task & Progress Tracker - Company Expenditure & Authorization Form - Developed 1 new Apps Script for financial transaction workflow automation. | - The development of the new Apps Script system is progressing more slowly due to MadVerse preparation and Leadership Camp tasks. - However, the implementation target remains unchanged for this year, while waiting for the EA to return from maternity leave. | -
Technology Optimization & Innovation | Integrated Database Implementation | To enhance operational data management by improving the company database and creating a centralized, integrated database design, in order to improve data management processes and support accurate, scalable, and data-driven decision-making. | Action: Improve the company database and create a centralized, integrated database design. Target: - Create 1 document outlining the database structure and design plan that centralizes and integrates existing databases. The Way: - Provide technical support and ensure the IT infrastructure is prepared for future implementation - Design the data architecture for the centralized and integrated database structure plan. - Develop roadmap for integrated database implementation. | 3 month(s) and 17 day(s) left | In Progress |  | Ongoing | Breakthrough | ITE | ITE | ITE, MNG, OPS | Yes | Program | Periodic | 1. Complexity Mid 2. Frequency Low 3. Execution Period Long | - Centralizes operational data to support analytics, reporting, and scalable data-driven decision-making. - Improves data integrity, governance, and access control across systems. - Provides a strong foundation for business intelligence, dashboards, and process automation. | - Requires specialized knowledge in data architecture and technical expertise. - Initial setup and integration effort can be complex and time-consuming. | - Improves cross-department data consistency and visibility. - Provides foundation for AI, predictive analytics, and supports scalable reporting automation. | - Misconfigured access controls or data mismanagement may lead to security or compliance issues. - Data quality issues may reduce analytics value. | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Technology Innovation | 2026-02-01 | 2026-12-31 |  | No Adjustment | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not started | N/A | - | - | Not started | N/A | - | - | In Progress | - https://lookerstudio.google.com/u/0/reporting/ae7f63ab-c2fb-40dd-bb58-0dbd23192585/page/XV5rF/edit - Data Integration - Pilot | - | - | In Progress | - [None for this month] | - | - | In Progress | - [None for this month] | - | - | In Progress | - [None for this month] | - | - | In Progress | - Template Migration - Implemented 1 new Apps Script for the Project Data Migration process in Operations to support the implementation of an integrated database that centralizes the project client masterlist from 2021 to 2024. | - | - | In Progress | - [None for this month] | - | -
Technology Optimization & Innovation | Technology Support for Service Development | To support the development of new company services by providing technology support and execution for service development initiatives, in order to enhance the company's service offerings and enable scalable service development. | Action: Provide technology support and execution for new service development initiatives. Target: - Create 1 document outlining technology and technical requirement for new service development. - Implement 100% of approved action plans to support new service development initiatives. The Way: - Collaborate with business development teams to identify technical requirements. - Configure systems and prepare IT infrastructure to support new service development as needed. - Resolve technical issues identified during new service development initiatives. | 3 month(s) and 17 day(s) left | Not started |  | Not Started | Breakthrough | ITE | ITE | ITE, MNG, OPS, GRW, EXP | Yes | Program | Periodic | 1. Complexity Mid 2. Frequency Mid 3. Execution Period Long | - Ensures IT readiness for new service launches. - Improves alignment between IT and business development teams. - Supports scalability of new services development. | - Potential skill gaps for new or specialized technologies. - Dependency on infrastructure readiness. | - Enables innovation-driven growth. - Improves service quality, scalability, and reliability. | - Potential technical limitations may delay new service launches. - Resource strain may occur when multiple initiatives are executed in parallel. | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Profitability - Business Development | 2026-02-01 | 2026-12-31 |  | No Adjustment | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | -
Technology Optimization & Innovation | Technology Optimization and Innovation Support | To support technology innovation and long-term business growth by providing technical support and execution for technology innovation initiatives, in order to optimize the company’s technology landscape, improve efficiency and scalability, and drive continuous innovation. | Action: Provide technical support and execution for technology innovation initiatives. Target: - Create 1 comprehensive document covering technology optimization and innovation, including research results and action plans. - Implement 100% of approved action plans to support technology optimization and innovation initiatives. The Way: - Collaborate with technology optimization teams to identify technical requirements. - Conduct research and exploration to support technology optimization and innovation as needed. - Resolve technical issues identified during technology optimization and innovation initiatives. | 3 month(s) and 17 day(s) left | In Progress |  | Ongoing | Breakthrough | ITE | ITE | ITE, MNG, OPS, GRW | Yes | Program | Annual | 1. Complexity Mid 2. Frequency Mid 3. Execution Period Long | - Processes are driven by company-specific needs and priorities. - Encourages innovation while aligning technology initiatives with long-term business strategy. - Improves operational efficiency, scalability, and overall competitiveness. | - Implementing new tools may involve high costs, budget constraints, and additional time and resources for research, pilots, and testing. - Returns on investment for emerging technologies may be uncertain | - Potential to access cost-efficient and affordable tools/technologies. - Opportunity to modernize the technology stack progressively. | - Employee resistance to adopting or adapting to new tools. - Potential compatibility and integration issues between new tools/technologies and existing systems. | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Technology Innovation | 2026-02-01 | 2026-12-31 |  | No Adjustment | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not started | N/A | - | - | Not started | N/A | - | - | In Progress | - Collaborative Project Tracker 2026 - Hola Holo, CRA, and Tech Optimization - OpenClaw Documentation | - | - | In Progress | - [None for this month] | - | - | In Progress | - [None for this month] | - | - | In Progress | - [None for this month] | - | - | In Progress | - [None for this month] | - | - | In Progress | - [None for this month] | - | -
Others | New IT Staff Recruitment | To strengthen the IT department’s capacity and establish a clear IT department structure by recruiting new IT staff, defining roles and responsibilities, and conducting a structured onboarding process, in order to support the company’s current and future technology needs and requirements. | Action: Recruit new IT staff and conduct a structured onboarding process. Target: - Create 1 document outlining IT staff roles and responsibilities and the onboarding process framework. - Hire and onboard 1 new IT staff. The Way: - Define roles and responsibilities for the new IT staff. - Coordinate the recruitment and onboarding process for new IT staff with the HRD department. - Support the onboarding process and conduct knowledge transfer sessions. | 2 month(s) and 1 day(s) left | In Progress |  | Ongoing | Breakthrough | ITE | ITE | ITE, HRD | Yes | Program | Occasional | 1. Complexity Low 2. Frequency Low 3. Execution Period Short | - Improves IT capacity and scalability of IT operations. - Clear roles, KPIs, and structure improve accountability. - Provides better technical support for both LeadGeeks and Alunara. | - Recruitment and onboarding require time and budget. - Knowledge transfer may be slow initially. | - Builds a scalable and future-ready IT organization. - Enables specialization and balanced workload distribution. | - Difficulty finding qualified candidates within budget. - Hiring delays impacting delivery timelines. | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Talent & Culture | 2026-06-01 | 2026-11-15 |  | Partial: Time-Bound | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-11-15 | Due to changes in the recruitment requirements and hiring process for the IT Staff position, the expected start date, which was originally July 1, 2026, has been postponed. As a result, the initial onboarding schedule has also been delayed. | N/A | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | In Progress | - New IT Staff Criteria and Recruitment - Technical Assessment - Create the recruitment and job requirements for the new IT staff position. - Create the technical assessments for IT staff recruitment, including the Technical Knowledge Assessment, Operational Case Study Assessment, Practical Technical Assessment, and AI Utilization & Productivity Assessment. | - | - Continue executing action items and tasks related to the IT Staff recruitment and hiring process. | In Progress | - New IT Staff Criteria and Recruitment - Technical Assessment - IT Staff - Technical Assessment Overall Score - User Interview Template - IT Staff - Create the recruitment and job requirements for the new IT staff position. - Create the technical assessment scoring framework and evaluate the candidates technical assessment results. - Review the candidates CVs for the IT Staff recruitment process. - Create the interview questions for the User Interview stage. | - | - Continue executing action items and tasks related to the IT Staff recruitment and hiring process. - Continue creating the IT Staff onboarding framework and plan. | In Progress | - IT Staff - Technical Assessment Overall Score - User Interview Template - IT Staff - Onboarding Kit Final 2026 - IT Staff - Grading - IT (2026) - Create and review the interview questions for the User Interview stage. - Conduct User Interviews for several IT Staff candidates. - Develop the new IT Staff onboarding framework. - Develop the new IT Staff grading system. | - | - Continue executing action items and tasks related to the IT Staff recruitment and hiring process. - Continue developing and reviewing the IT Staff onboarding framework and IT Staff grading system with the Managing Director (MD). | In Progress | - Onboarding Kit Final 2026 - IT Staff - Grading - IT (2026) - Develop the new IT Staff onboarding framework. - Develop the new IT Staff grading system. - Hire and select a new IT Staff after completing the recruitment process. | - | - Continue the onboarding process for the selected new IT Staff over the next three months.
Others | IT Department PMS Implementation | To implement a structured Performance Management System (PMS) within the IT department by defining measurable KPIs and monitoring performance evaluation processes, in order to ensure consistent performance monitoring and improve accountability. | Action: Define and monitor a structured Performance Management System (PMS) within the IT department. Target: - Develop 1 IT Department PMS framework document. The Way: - Define IT roles and responsibilities into measurable KPIs. - Coordinate with HRD department to align the PMS with company standards. - Socialize PMS guidelines to IT department members. - Monitor PMS effectiveness and improve KPIs based on evaluation outcomes. | 3 month(s) and 17 day(s) left | Not started |  | Not Started | Breakthrough | ITE | ITE | ITE, MNG, HRD | Yes | Program | Periodic | 1. Complexity Low 2. Frequency Mid 3. Execution Period Long | - Establishes clear and measurable KPIs for IT roles, improving performance transparency. - Improves accountability and consistency in performance evaluation across the IT department. - Aligns individual IT performance with departmental and company objectives. | - Initial KPI definition and PMS setup require time and cross-department coordination. - Initial resistance or learning curve from IT staff adapting to a new evaluation system. | - Supports employee development through structured performance feedback and career development. - Enables data-driven decision-making for promotions, training, and resource allocation. | - Lack of management commitment may reduce PMS effectiveness and adoption. - Misaligned or poorly defined KPIs may lead to inaccurate performance assessment. | Budget: -YES Human resource: -YES Time: -YES Technology: -YES | Unavailable resources: - Plan moving forward: - | Company Establishment - Talent & Culture | 2026-02-01 | 2026-12-31 |  | No Adjustment | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | - | Not started | N/A | - | -
Formulas:
Accomplishment Status = IF(ISBLANK([Department Functions]:A21), "", IF(NOT(ISBLANK([Date of Accomplishment]:G21)), IF([Date of Accomplishment]:G21 < [End date (Time bound)]:Y21, "Completed: Early", IF([Date of Accomplishment]:G21 = [End date (Time bound)]:Y21, "Completed: On Time", "Completed: Late") ), IF(TODAY() < [Start date (Time bound)]:X21, "Not Started", IF(TODAY() <= [End date (Time bound)]:Y21, "Ongoing", "Overdue") ) ) )

## Drop Down
Status | Completion Status | Company Priority | Company Focus | Departments | Department Code | Goals Type | Collaboration | Type | Period | Accomplishment Status | Periodic Adjustment | Department Functions (MNG) | Dept Functions (FAC)
Not started | Complete | Company Profitability | Company Profitability - Customer Retention | Management Office | MNG | Breakthrough | No | Program | Annual | Not Started | No Adjustment | 1. Strategic Direction and Enterprise Planning | 1. Financial Management (Finance)
In Progress | Incomplete | Company Profitability | Company Profitability - Business Development | Operations | OPS | Improvement | Yes | Event | Periodic | Ongoing | Total: Deletion | 2. Advancement and Change Governance | 2. Financial Accounting (Accounting)
Completed |  | Company Profitability | Company Profitability - Customer Acquisition | Growth | GRW | Routine |  | Training (Internal) | Occasional | Overdue | Partial: Specific | 3. Financial Stewardship and Capital Strategy | 3. Management Accounting (Controlling)
Postponed |  | Company Profitability | Company Profitability - Strong Financial and Risk Management | Experience | EXP |  |  | Training (Cross-Departmental) |  | Completed: Early | Partial: Measurable | 4. Executive Leadership and Organizational Culture | 4. Tax Management (Compliance & Strategy)
Cancelled |  | Company Establishment | Company Establishment - Talent & Culture | Human Resources and Development | HRD |  |  |  |  | Completed: On Time | Partial: Attainable | 5. Governance, Risk, and Compliance Oversight | 5. Systems & Policy Management
|  | Company Establishment | Company Establishment - Technology Innovation | Finance and Accounting | FAC |  |  |  |  | Completed: Late | Partial: Relevant | 6. Enterprise Operations Oversight
|  | Company Establishment | Company Establishment - Organizational Structure | Information and Technology | ITE | [5 empty] | Partial: Time-Bound | 7. Market Leadership and Customer Focus
|  | Company Establishment | Company Establishment - Branding, Communication & Experience | Fulfillment by Amazon | FBA | [5 empty] | Total: Addition | 8. Stakeholder and Ecosystem Engagement
Budget Adjustment